## TASK
task_code | status_code | wbs_id | wbs_name | task_name | target_drtn_hr_cnt | act_drtn_hr_cnt | start_date | end_date | pred_list | resource_code_list | resource_list | ACWP | critical_flag | delete_record_flag
Activity ID | Activity Status | WBS Code | (*)WBS Name | Activity Name | Original Duration(h) | (*)Actual Duration(h) | (*)Start | (*)Finish | (*)Predecessors | (*)Resource IDs | (*)Resources | (*)Actual Cost($) | (*)Critical | Delete This Row
WPICON042 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Soil Testing & Backfill | 6 | 6 | 01-Apr-24 | 07-Apr-24 | WPICON041 | MTR | Material | 9605 | TRUE | NO
WPICON039 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Wearing Course Application | 5 | 5 | 01-Jan-23 | 06-Jan-23 | WPICON038 | LBR | Labor | 2568 | TRUE | NO
WPICON050 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Base Grading | 8 | 8 | 01-Jun-23 | 09-Jun-23 | WPICON049 | MTR | Material | 2188 | TRUE | NO
WPICON146 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Soil Testing & Backfill | 8 | 8 | 02-Apr-23 | 10-Apr-23 | WPICON145 | MTR | Material | 6049 | TRUE | NO
WPICON011 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Base Grading | 9 | 9 | 02-Aug-24 | 11-Aug-24 | WPICON010 | MTR | Material | 3770 | TRUE | NO
WPICON113 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Waterproofing | 3 | 3 | 02-Dec-23 | 05-Dec-23 | WPICON112 | LBR | Labor | 3403 | TRUE | NO
WPICON148 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Steel Fabrication | 4 | 4 | 02-Dec-23 | 06-Dec-23 | WPICON147 | LBR | Labor | 2789 | TRUE | NO
WPICON023 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Civil Completion & Curing | 10 | 10 | 02-Feb-24 | 12-Feb-24 | WPICON022 | LBR | Labor | 8477 | TRUE | NO
WPICON145 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Excavation Work | 9 | 9 | 02-Jan-24 | 11-Jan-24 | WPICON144 | LBR | Labor | 2033 | TRUE | NO
WPICON091 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Wearing Course Application | 10 | 10 | 02-Jul-24 | 12-Jul-24 | WPICON090 | LBR | Labor | 8320 | TRUE | NO
WPICON118 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Site Survey & Demarcation | 7 | 7 | 02-Mar-23 | 09-Mar-23 | WPICON117 | LBR | Labor | 7937 | TRUE | NO
WPICON084 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Concrete Pouring - Basement | 9 | 9 | 02-Sep-23 | 11-Sep-23 | WPICON083 | LBR | Labor | 891 | TRUE | NO
WPICON040 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Site Survey & Demarcation | 9 | 9 | 03-Apr-23 | 12-Apr-23 | WPICON039 | LBR | Labor | 1515 | TRUE | NO
WPICON117 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Wearing Course Application | 7 | 7 | 03-Apr-23 | 10-Apr-23 | WPICON116 | LBR | Labor | 1254 | TRUE | NO
WPICON044 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Steel Fabrication | 6 | 6 | 03-Apr-24 | 09-Apr-24 | WPICON043 | LBR | Labor | 8748 | TRUE | NO
WPICON032 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Concrete Pouring - Basement | 7 | 7 | 03-Aug-23 | 10-Aug-23 | WPICON031 | LBR | Labor | 7912 | TRUE | NO
WPICON083 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Steel Fabrication | 8 | 8 | 03-May-23 | 11-May-23 | WPICON082 | LBR | Labor | 1084 | TRUE | NO
WPICON030 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Foundation Construction | 9 | 9 | 03-May-24 | 12-May-24 | WPICON029 | LBR | Labor | 3766 | TRUE | NO
WPICON067 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Excavation Work | 5 | 5 | 03-May-24 | 08-May-24 | WPICON066 | LBR | Labor | 4803 | TRUE | NO
WPICON009 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Waterproofing | 6 | 6 | 03-Nov-23 | 09-Nov-23 | WPICON008 | LBR | Labor | 3381 | TRUE | NO
WPICON081 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Soil Testing & Backfill | 6 | 6 | 04-Feb-23 | 10-Feb-23 | WPICON080 | MTR | Material | 6576 | TRUE | NO
WPICON004 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Foundation Construction | 5 | 5 | 04-Jan-24 | 09-Jan-24 | WPICON003 | LBR | Labor | 3222 | TRUE | NO
WPICON127 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Civil Completion & Curing | 8 | 8 | 04-Jul-23 | 12-Jul-23 | WPICON126 | LBR | Labor | 660 | TRUE | NO
WPICON006 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Concrete Pouring - Basement | 8 | 8 | 05-Aug-23 | 13-Aug-23 | WPICON005 | LBR | Labor | 1590 | TRUE | NO
WPICON143 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Wearing Course Application | 9 | 9 | 05-Aug-23 | 14-Aug-23 | WPICON142 | LBR | Labor | 8754 | TRUE | NO
WPICON119 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Excavation Work | 6 | 6 | 05-Aug-24 | 11-Aug-24 | WPICON118 | LBR | Labor | 6543 | TRUE | NO
WPICON129 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Sub-Base Filling | 7 | 7 | 05-Dec-23 | 12-Dec-23 | WPICON128 | LBR | Labor | 1028 | TRUE | NO
WPICON120 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Soil Testing & Backfill | 4 | 4 | 05-Jun-24 | 09-Jun-24 | WPICON119 | MTR | Material | 3753 | TRUE | NO
WPICON137 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Concrete Pouring - 1st Floor | 3 | 3 | 05-Jun-24 | 08-Jun-24 | WPICON136 | LBR | Labor | 1507 | TRUE | NO
WPICON086 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Concrete Pouring - 2nd Floor | 9 | 9 | 05-Mar-24 | 14-Mar-24 | WPICON085 | LBR | Labor | 3671 | TRUE | NO
WPICON020 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Concrete Pouring - 1st Floor | 5 | 5 | 05-Sep-23 | 10-Sep-23 | WPICON019 | LBR | Labor | 2122 | TRUE | NO
WPICON062 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Civil Completion & Curing | 8 | 8 | 06-Apr-24 | 14-Apr-24 | WPICON061 | LBR | Labor | 2156 | TRUE | NO
WPICON150 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Concrete Pouring - 1st Floor | 8 | 8 | 06-Apr-24 | 14-Apr-24 | WPICON149 | LBR | Labor | 4777 | TRUE | NO
WPICON082 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Foundation Construction | 4 | 4 | 06-Feb-23 | 10-Feb-23 | WPICON081 | LBR | Labor | 5178 | TRUE | NO
WPICON015 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Excavation Work | 7 | 7 | 06-Jan-23 | 13-Jan-23 | WPICON014 | LBR | Labor | 5096 | TRUE | NO
WPICON138 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Concrete Pouring - 2nd Floor | 3 | 3 | 06-Jul-24 | 09-Jul-24 | WPICON137 | LBR | Labor | 5175 | TRUE | NO
WPICON116 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Sub-Base Filling | 6 | 6 | 07-Dec-23 | 13-Dec-23 | WPICON115 | LBR | Labor | 7739 | TRUE | NO
WPICON049 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Civil Completion & Curing | 4 | 4 | 07-May-24 | 11-May-24 | WPICON048 | LBR | Labor | 8566 | TRUE | NO
WPICON078 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Wearing Course Application | 10 | 10 | 07-May-24 | 17-May-24 | WPICON077 | LBR | Labor | 1432 | TRUE | NO
WPICON141 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Base Grading | 5 | 5 | 07-May-24 | 12-May-24 | WPICON140 | MTR | Material | 3945 | TRUE | NO
WPICON122 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Steel Fabrication | 3 | 3 | 08-Jan-23 | 11-Jan-23 | WPICON121 | LBR | Labor | 6548 | TRUE | NO
WPICON140 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Civil Completion & Curing | 10 | 10 | 08-Jul-24 | 18-Jul-24 | WPICON139 | LBR | Labor | 2043 | TRUE | NO
WPICON022 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Waterproofing | 9 | 9 | 08-Jun-23 | 17-Jun-23 | WPICON021 | LBR | Labor | 4524 | TRUE | NO
WPICON037 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Base Grading | 9 | 9 | 08-Mar-23 | 17-Mar-23 | WPICON036 | MTR | Material | 928 | TRUE | NO
WPICON147 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Foundation Construction | 3 | 3 | 08-May-23 | 11-May-23 | WPICON146 | LBR | Labor | 6972 | TRUE | NO
WPICON065 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Wearing Course Application | 9 | 9 | 08-Nov-23 | 17-Nov-23 | WPICON064 | LBR | Labor | 8583 | TRUE | NO
WPICON046 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Concrete Pouring - 1st Floor | 7 | 7 | 09-Apr-23 | 16-Apr-23 | WPICON045 | LBR | Labor | 3113 | TRUE | NO
WPICON061 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Waterproofing | 8 | 8 | 09-Dec-23 | 17-Dec-23 | WPICON060 | LBR | Labor | 5724 | TRUE | NO
WPICON038 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Sub-Base Filling | 8 | 8 | 09-Feb-24 | 17-Feb-24 | WPICON037 | LBR | Labor | 934 | TRUE | NO
WPICON100 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Waterproofing | 7 | 7 | 09-Jan-24 | 16-Jan-24 | WPICON099 | LBR | Labor | 3061 | TRUE | NO
WPICON068 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Soil Testing & Backfill | 3 | 3 | 09-Mar-24 | 12-Mar-24 | WPICON067 | MTR | Material | 937 | TRUE | NO
WPICON033 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Concrete Pouring - 1st Floor | 7 | 7 | 10-Apr-24 | 17-Apr-24 | WPICON032 | LBR | Labor | 4205 | TRUE | NO
WPICON144 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Site Survey & Demarcation | 5 | 5 | 10-Aug-24 | 15-Aug-24 | WPICON143 | LBR | Labor | 3259 | TRUE | NO
WPICON094 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Soil Testing & Backfill | 4 | 4 | 10-Feb-24 | 14-Feb-24 | WPICON093 | MTR | Material | 1263 | TRUE | NO
WPICON058 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Concrete Pouring - Basement | 10 | 10 | 10-Jul-23 | 20-Jul-23 | WPICON057 | LBR | Labor | 4654 | TRUE | NO
WPICON136 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Concrete Pouring - Basement | 6 | 6 | 10-Jun-24 | 16-Jun-24 | WPICON135 | LBR | Labor | 6299 | TRUE | NO
WPICON001 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Site Survey & Demarcation | 7 | 7 | 11-Dec-23 | 18-Dec-23 |  | LBR | Labor | 2847 | TRUE | NO
WPICON123 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Concrete Pouring - Basement | 3 | 3 | 11-Jun-24 | 14-Jun-24 | WPICON122 | LBR | Labor | 3538 | TRUE | NO
WPICON021 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Concrete Pouring - 2nd Floor | 7 | 7 | 11-Nov-23 | 18-Nov-23 | WPICON020 | LBR | Labor | 8484 | TRUE | NO
WPICON054 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Excavation Work | 7 | 7 | 11-Sep-23 | 18-Sep-23 | WPICON053 | LBR | Labor | 4458 | TRUE | NO
WPICON045 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Concrete Pouring - Basement | 9 | 9 | 12-Aug-23 | 21-Aug-23 | WPICON044 | LBR | Labor | 642 | TRUE | NO
WPICON072 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Concrete Pouring - 1st Floor | 9 | 9 | 12-Jul-23 | 21-Jul-23 | WPICON071 | LBR | Labor | 8729 | TRUE | NO
WPICON064 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Sub-Base Filling | 10 | 10 | 12-Jun-24 | 22-Jun-24 | WPICON063 | LBR | Labor | 3938 | TRUE | NO
WPICON114 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Civil Completion & Curing | 4 | 4 | 12-May-23 | 16-May-23 | WPICON113 | LBR | Labor | 4758 | TRUE | NO
WPICON085 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Concrete Pouring - 1st Floor | 4 | 4 | 12-May-24 | 16-May-24 | WPICON084 | LBR | Labor | 7665 | TRUE | NO
WPICON055 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Soil Testing & Backfill | 4 | 4 | 12-Nov-23 | 16-Nov-23 | WPICON054 | MTR | Material | 6066 | TRUE | NO
WPICON090 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Sub-Base Filling | 7 | 7 | 12-Nov-23 | 19-Nov-23 | WPICON089 | LBR | Labor | 4449 | TRUE | NO
WPICON079 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Site Survey & Demarcation | 10 | 10 | 12-Sep-23 | 22-Sep-23 | WPICON078 | LBR | Labor | 2060 | TRUE | NO
WPICON125 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Concrete Pouring - 2nd Floor | 9 | 9 | 12-Sep-23 | 21-Sep-23 | WPICON124 | LBR | Labor | 7496 | TRUE | NO
WPICON080 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Excavation Work | 9 | 9 | 13-Feb-24 | 22-Feb-24 | WPICON079 | LBR | Labor | 5694 | TRUE | NO
WPICON010 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Civil Completion & Curing | 8 | 8 | 13-Jan-23 | 21-Jan-23 | WPICON009 | LBR | Labor | 7009 | TRUE | NO
WPICON107 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Soil Testing & Backfill | 9 | 9 | 13-Jun-24 | 22-Jun-24 | WPICON106 | MTR | Material | 5322 | TRUE | NO
WPICON059 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Concrete Pouring - 1st Floor | 3 | 3 | 13-Sep-23 | 16-Sep-23 | WPICON058 | LBR | Labor | 7703 | TRUE | NO
WPICON095 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Foundation Construction | 6 | 6 | 14-Apr-24 | 20-Apr-24 | WPICON094 | LBR | Labor | 7157 | TRUE | NO
WPICON112 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Concrete Pouring - 2nd Floor | 7 | 7 | 14-Aug-24 | 21-Aug-24 | WPICON111 | LBR | Labor | 1435 | TRUE | NO
WPICON066 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Site Survey & Demarcation | 6 | 6 | 14-Jul-24 | 20-Jul-24 | WPICON065 | LBR | Labor | 8916 | TRUE | NO
WPICON012 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Sub-Base Filling | 3 | 3 | 14-Jun-23 | 17-Jun-23 | WPICON011 | LBR | Labor | 8854 | TRUE | NO
WPICON099 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Concrete Pouring - 2nd Floor | 5 | 5 | 14-Jun-24 | 19-Jun-24 | WPICON098 | LBR | Labor | 2078 | TRUE | NO
WPICON149 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Concrete Pouring - Basement | 8 | 8 | 14-Mar-23 | 22-Mar-23 | WPICON148 | LBR | Labor | 802 | TRUE | NO
WPICON076 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Base Grading | 5 | 5 | 14-Oct-23 | 19-Oct-23 | WPICON075 | MTR | Material | 2662 | TRUE | NO
WPICON132 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Excavation Work | 10 | 10 | 14-Sep-23 | 24-Sep-23 | WPICON131 | LBR | Labor | 2700 | TRUE | NO
WPICON017 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Foundation Construction | 7 | 7 | 15-Apr-23 | 22-Apr-23 | WPICON016 | LBR | Labor | 4127 | TRUE | NO
WPICON121 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Foundation Construction | 6 | 6 | 15-Feb-23 | 21-Feb-23 | WPICON120 | LBR | Labor | 4851 | TRUE | NO
WPICON063 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Base Grading | 6 | 6 | 15-Jun-24 | 21-Jun-24 | WPICON062 | MTR | Material | 2907 | TRUE | NO
WPICON108 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Foundation Construction | 6 | 6 | 15-May-23 | 21-May-23 | WPICON107 | LBR | Labor | 9515 | TRUE | NO
WPICON034 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Concrete Pouring - 2nd Floor | 5 | 5 | 15-Oct-23 | 20-Oct-23 | WPICON033 | LBR | Labor | 9005 | TRUE | NO
WPICON070 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Steel Fabrication | 8 | 8 | 16-Jul-24 | 24-Jul-24 | WPICON069 | LBR | Labor | 6686 | TRUE | NO
WPICON098 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Concrete Pouring - 1st Floor | 8 | 8 | 16-Mar-24 | 24-Mar-24 | WPICON097 | LBR | Labor | 7801 | TRUE | NO
WPICON131 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Site Survey & Demarcation | 10 | 10 | 16-Nov-23 | 26-Nov-23 | WPICON130 | LBR | Labor | 4152 | TRUE | NO
WPICON005 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Steel Fabrication | 10 | 10 | 17-Apr-24 | 27-Apr-24 | WPICON004 | LBR | Labor | 1732 | TRUE | NO
WPICON134 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Foundation Construction | 10 | 10 | 17-Feb-23 | 27-Feb-23 | WPICON133 | LBR | Labor | 5827 | TRUE | NO
WPICON101 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Civil Completion & Curing | 6 | 6 | 17-Jun-24 | 23-Jun-24 | WPICON100 | LBR | Labor | 735 | TRUE | NO
WPICON105 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Site Survey & Demarcation | 5 | 5 | 17-Oct-23 | 22-Oct-23 | WPICON104 | LBR | Labor | 3325 | TRUE | NO
WPICON115 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Base Grading | 10 | 10 | 18-Apr-23 | 28-Apr-23 | WPICON114 | MTR | Material | 3844 | TRUE | NO
WPICON097 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Concrete Pouring - Basement | 9 | 9 | 18-Jul-24 | 27-Jul-24 | WPICON096 | LBR | Labor | 3119 | TRUE | NO
WPICON087 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Waterproofing | 10 | 10 | 19-Apr-23 | 29-Apr-23 | WPICON086 | LBR | Labor | 9989 | TRUE | NO
WPICON027 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Site Survey & Demarcation | 6 | 6 | 19-Jan-24 | 25-Jan-24 | WPICON026 | LBR | Labor | 1359 | TRUE | NO
WPICON139 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Waterproofing | 7 | 7 | 20-Jun-23 | 27-Jun-23 | WPICON138 | LBR | Labor | 8620 | TRUE | NO
WPICON109 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Steel Fabrication | 7 | 7 | 20-May-24 | 27-May-24 | WPICON108 | LBR | Labor | 3268 | TRUE | NO
WPICON013 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Wearing Course Application | 6 | 6 | 20-Sep-23 | 26-Sep-23 | WPICON012 | LBR | Labor | 1139 | TRUE | NO
WPICON029 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Soil Testing & Backfill | 6 | 6 | 21-Apr-24 | 27-Apr-24 | WPICON028 | MTR | Material | 5271 | TRUE | NO
WPICON056 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Foundation Construction | 3 | 3 | 21-Apr-24 | 24-Apr-24 | WPICON055 | LBR | Labor | 1985 | TRUE | NO
WPICON073 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Concrete Pouring - 2nd Floor | 7 | 7 | 21-Jan-24 | 28-Jan-24 | WPICON072 | LBR | Labor | 8565 | TRUE | NO
WPICON142 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Sub-Base Filling | 10 | 10 | 21-Jul-23 | 31-Jul-23 | WPICON141 | LBR | Labor | 5961 | TRUE | NO
WPICON007 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Concrete Pouring - 1st Floor | 5 | 5 | 21-Jul-24 | 26-Jul-24 | WPICON006 | LBR | Labor | 3238 | TRUE | NO
WPICON093 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Excavation Work | 7 | 7 | 21-Jun-24 | 28-Jun-24 | WPICON092 | LBR | Labor | 4250 | TRUE | NO
WPICON060 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Concrete Pouring - 2nd Floor | 6 | 6 | 21-Mar-24 | 27-Mar-24 | WPICON059 | LBR | Labor | 8521 | TRUE | NO
WPICON028 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Excavation Work | 10 | 10 | 21-May-23 | 31-May-23 | WPICON027 | LBR | Labor | 8592 | TRUE | NO
WPICON135 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Steel Fabrication | 3 | 3 | 21-Sep-23 | 24-Sep-23 | WPICON134 | LBR | Labor | 2822 | TRUE | NO
WPICON024 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Base Grading | 10 | 10 | 22-Feb-24 | 03-Mar-24 | WPICON023 | MTR | Material | 3256 | TRUE | NO
WPICON071 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Concrete Pouring - Basement | 5 | 5 | 22-Jul-23 | 27-Jul-23 | WPICON070 | LBR | Labor | 4844 | TRUE | NO
WPICON092 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Site Survey & Demarcation | 5 | 5 | 23-Apr-24 | 28-Apr-24 | WPICON091 | LBR | Labor | 6999 | TRUE | NO
WPICON053 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Site Survey & Demarcation | 5 | 5 | 23-Feb-24 | 28-Feb-24 | WPICON052 | LBR | Labor | 764 | TRUE | NO
WPICON104 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Wearing Course Application | 5 | 5 | 23-Feb-24 | 28-Feb-24 | WPICON103 | LBR | Labor | 7854 | TRUE | NO
WPICON128 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Base Grading | 9 | 9 | 23-Jan-23 | 01-Feb-23 | WPICON127 | MTR | Material | 8542 | TRUE | NO
WPICON026 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Wearing Course Application | 5 | 5 | 23-May-23 | 28-May-23 | WPICON025 | LBR | Labor | 4068 | TRUE | NO
WPICON077 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Sub-Base Filling | 9 | 9 | 23-May-24 | 01-Jun-24 | WPICON076 | LBR | Labor | 4545 | TRUE | NO
WPICON051 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Sub-Base Filling | 8 | 8 | 23-Nov-23 | 01-Dec-23 | WPICON050 | LBR | Labor | 9884 | TRUE | NO
WPICON110 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Concrete Pouring - Basement | 8 | 8 | 24-Apr-24 | 02-May-24 | WPICON109 | LBR | Labor | 7682 | TRUE | NO
WPICON103 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Sub-Base Filling | 7 | 7 | 24-Nov-23 | 01-Dec-23 | WPICON102 | LBR | Labor | 5636 | TRUE | NO
WPICON008 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Concrete Pouring - 2nd Floor | 6 | 6 | 25-Apr-23 | 01-May-23 | WPICON007 | LBR | Labor | 1927 | TRUE | NO
WPICON047 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Concrete Pouring - 2nd Floor | 7 | 7 | 25-Apr-23 | 02-May-23 | WPICON046 | LBR | Labor | 9670 | TRUE | NO
WPICON035 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Waterproofing | 7 | 7 | 25-Feb-24 | 03-Mar-24 | WPICON034 | LBR | Labor | 1452 | TRUE | NO
WPICON130 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Wearing Course Application | 7 | 7 | 25-Jul-23 | 01-Aug-23 | WPICON129 | LBR | Labor | 6166 | TRUE | NO
WPICON031 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Steel Fabrication | 3 | 3 | 25-Jul-24 | 28-Jul-24 | WPICON030 | LBR | Labor | 3174 | TRUE | NO
WPICON075 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Civil Completion & Curing | 5 | 5 | 25-Jun-23 | 30-Jun-23 | WPICON074 | LBR | Labor | 4676 | TRUE | NO
WPICON074 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Waterproofing | 9 | 9 | 25-Jun-24 | 04-Jul-24 | WPICON073 | LBR | Labor | 5205 | TRUE | NO
WPICON126 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Waterproofing | 7 | 7 | 25-May-24 | 01-Jun-24 | WPICON125 | LBR | Labor | 5086 | TRUE | NO
WPICON069 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Foundation Construction | 5 | 5 | 25-Oct-23 | 30-Oct-23 | WPICON068 | LBR | Labor | 1001 | TRUE | NO
WPICON102 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Base Grading | 4 | 4 | 26-Apr-23 | 30-Apr-23 | WPICON101 | MTR | Material | 3990 | TRUE | NO
WPICON019 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Concrete Pouring - Basement | 4 | 4 | 26-Apr-24 | 30-Apr-24 | WPICON018 | LBR | Labor | 7265 | TRUE | NO
WPICON052 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Wearing Course Application | 8 | 8 | 26-Feb-23 | 06-Mar-23 | WPICON051 | LBR | Labor | 6497 | TRUE | NO
WPICON124 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Concrete Pouring - 1st Floor | 4 | 4 | 27-Apr-23 | 01-May-23 | WPICON123 | LBR | Labor | 9988 | TRUE | NO
WPICON016 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Soil Testing & Backfill | 4 | 4 | 27-Feb-23 | 03-Mar-23 | WPICON015 | MTR | Material | 1663 | TRUE | NO
WPICON111 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Concrete Pouring - 1st Floor | 4 | 4 | 27-May-23 | 31-May-23 | WPICON110 | LBR | Labor | 4720 | TRUE | NO
WPICON096 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Steel Fabrication | 5 | 5 | 28-Apr-23 | 03-May-23 | WPICON095 | LBR | Labor | 1013 | TRUE | NO
WPICON043 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Foundation Construction | 10 | 10 | 28-Feb-23 | 10-Mar-23 | WPICON042 | LBR | Labor | 1170 | TRUE | NO
WPICON025 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Sub-Base Filling | 4 | 4 | 28-Jun-23 | 02-Jul-23 | WPICON024 | LBR | Labor | 6721 | TRUE | NO
WPICON048 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Waterproofing | 4 | 4 | 28-Mar-23 | 01-Apr-23 | WPICON047 | LBR | Labor | 4284 | TRUE | NO
WPICON106 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Excavation Work | 9 | 9 | 28-May-24 | 06-Jun-24 | WPICON105 | LBR | Labor | 4823 | TRUE | NO
WPICON002 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Excavation Work | 3 | 3 | 29-Apr-23 | 02-May-23 | WPICON001 | LBR | Labor | 2394 | TRUE | NO
WPICON036 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Civil Completion & Curing | 3 | 3 | 29-Apr-24 | 02-May-24 | WPICON035 | LBR | Labor | 5760 | TRUE | NO
WPICON041 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Excavation Work | 4 | 4 | 29-Aug-23 | 02-Sep-23 | WPICON040 | LBR | Labor | 9551 | TRUE | NO
WPICON057 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Steel Fabrication | 9 | 9 | 29-Jul-24 | 07-Aug-24 | WPICON056 | LBR | Labor | 4383 | TRUE | NO
WPICON133 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Soil Testing & Backfill | 9 | 9 | 29-Jul-24 | 07-Aug-24 | WPICON132 | MTR | Material | 4878 | TRUE | NO
WPICON014 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Site Survey & Demarcation | 8 | 8 | 29-Jun-23 | 07-Jul-23 | WPICON013 | LBR | Labor | 1556 | TRUE | NO
WPICON089 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Base Grading | 7 | 7 | 29-May-23 | 05-Jun-23 | WPICON088 | MTR | Material | 1003 | TRUE | NO
WPICON088 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Civil Completion & Curing | 7 | 7 | 30-Jul-24 | 06-Aug-24 | WPICON087 | LBR | Labor | 668 | TRUE | NO
WPICON003 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Soil Testing & Backfill | 10 | 10 | 30-Mar-24 | 09-Apr-24 | WPICON002 | MTR | Material | 9364 | TRUE | NO
WPICON018 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Steel Fabrication | 4 | 4 | 31-Jul-23 | 04-Aug-23 | WPICON017 | LBR | Labor | 6052 | TRUE | NO
WPIELC038 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install CCTV System | 4 | 4 | 01-Apr-23 | 05-Apr-23 | WPIELC037 | LBR | Labor | 6238 | FALSE | NO
WPIELC056 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Electrical Commissioning | 6 | 6 | 01-Aug-23 | 07-Aug-23 | WPIELC055 | LBR | Labor | 7441 | FALSE | NO
WPIELC073 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Cable Tray Installation | 4 | 4 | 01-Jun-23 | 05-Jun-23 | WPIELC072 | LBR | Labor | 5840 | FALSE | NO
WPIELC090 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Lighting System Installation | 6 | 6 | 01-Mar-24 | 07-Mar-24 | WPIELC089 | LBR | Labor | 8391 | FALSE | NO
WPIELC045 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Automation Wiring | 9 | 9 | 01-Sep-23 | 10-Sep-23 | WPIELC044 | LBR | Labor | 2960 | FALSE | NO
WPIELC065 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Cable Tray Installation | 5 | 5 | 02-Feb-24 | 07-Feb-24 | WPIELC064 | LBR | Labor | 6678 | FALSE | NO
WPIELC097 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Cable Tray Installation | 6 | 6 | 02-Mar-23 | 08-Mar-23 | WPIELC096 | LBR | Labor | 3020 | FALSE | NO
WPIELC009 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Cable Tray Installation | 4 | 4 | 03-Aug-24 | 07-Aug-24 | WPIELC008 | LBR | Labor | 702 | FALSE | NO
WPIELC015 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | 120kW Solar Panel Setup | 6 | 6 | 03-Dec-23 | 09-Dec-23 | WPIELC014 | LBR | Labor | 6051 | FALSE | NO
WPIELC086 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install CCTV System | 10 | 10 | 03-Feb-23 | 13-Feb-23 | WPIELC085 | LBR | Labor | 1497 | FALSE | NO
WPIELC094 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install CCTV System | 10 | 10 | 03-Feb-24 | 13-Feb-24 | WPIELC093 | LBR | Labor | 9928 | FALSE | NO
WPIELC093 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Automation Wiring | 9 | 9 | 04-Feb-24 | 13-Feb-24 | WPIELC092 | LBR | Labor | 533 | FALSE | NO
WPIELC011 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Switchboards Installation | 9 | 9 | 04-Jan-24 | 13-Jan-24 | WPIELC010 | LBR | Labor | 2622 | FALSE | NO
WPIELC059 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Switchboards Installation | 6 | 6 | 05-Aug-23 | 11-Aug-23 | WPIELC058 | LBR | Labor | 5868 | FALSE | NO
WPIELC070 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install CCTV System | 4 | 4 | 06-Apr-24 | 10-Apr-24 | WPIELC069 | LBR | Labor | 1899 | FALSE | NO
WPIELC077 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Automation Wiring | 10 | 10 | 06-Apr-24 | 16-Apr-24 | WPIELC076 | LBR | Labor | 1946 | FALSE | NO
WPIELC042 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Lighting System Installation | 10 | 10 | 06-Jul-24 | 16-Jul-24 | WPIELC041 | LBR | Labor | 9873 | FALSE | NO
WPIELC002 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Lighting System Installation | 10 | 10 | 06-Jun-23 | 16-Jun-23 | WPIELC001 | LBR | Labor | 2368 | FALSE | NO
WPIELC024 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Electrical Commissioning | 4 | 4 | 06-Sep-23 | 10-Sep-23 | WPIELC023 | LBR | Labor | 2113 | FALSE | NO
WPIELC067 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Switchboards Installation | 4 | 4 | 06-Sep-23 | 10-Sep-23 | WPIELC066 | LBR | Labor | 9476 | FALSE | NO
WPIELC080 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Electrical Commissioning | 9 | 9 | 07-May-24 | 16-May-24 | WPIELC079 | LBR | Labor | 809 | FALSE | NO
WPIELC017 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Cable Tray Installation | 10 | 10 | 07-Nov-23 | 17-Nov-23 | WPIELC016 | LBR | Labor | 5671 | FALSE | NO
WPIELC076 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Power Panel Setup | 6 | 6 | 08-Dec-23 | 14-Dec-23 | WPIELC075 | LBR | Labor | 4399 | FALSE | NO
WPIELC048 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Electrical Commissioning | 4 | 4 | 08-Jun-24 | 12-Jun-24 | WPIELC047 | LBR | Labor | 7292 | FALSE | NO
WPIELC084 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Power Panel Setup | 4 | 4 | 08-Nov-23 | 12-Nov-23 | WPIELC083 | LBR | Labor | 1563 | FALSE | NO
WPIELC095 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | 120kW Solar Panel Setup | 9 | 9 | 09-Apr-24 | 18-Apr-24 | WPIELC094 | LBR | Labor | 4014 | FALSE | NO
WPIELC019 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Switchboards Installation | 6 | 6 | 09-Dec-23 | 15-Dec-23 | WPIELC018 | LBR | Labor | 8847 | FALSE | NO
WPIELC016 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Electrical Commissioning | 4 | 4 | 10-Apr-24 | 14-Apr-24 | WPIELC015 | LBR | Labor | 7744 | FALSE | NO
WPIELC071 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | 120kW Solar Panel Setup | 6 | 6 | 10-Feb-24 | 16-Feb-24 | WPIELC070 | LBR | Labor | 8835 | FALSE | NO
WPIELC022 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install CCTV System | 6 | 6 | 10-Jan-23 | 16-Jan-23 | WPIELC021 | LBR | Labor | 7365 | FALSE | NO
WPIELC043 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Switchboards Installation | 5 | 5 | 10-Jul-24 | 15-Jul-24 | WPIELC042 | LBR | Labor | 3145 | FALSE | NO
WPIELC069 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Automation Wiring | 6 | 6 | 12-Aug-23 | 18-Aug-23 | WPIELC068 | LBR | Labor | 9504 | FALSE | NO
WPIELC004 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Power Panel Setup | 10 | 10 | 12-Aug-24 | 22-Aug-24 | WPIELC003 | LBR | Labor | 8366 | FALSE | NO
WPIELC099 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Switchboards Installation | 10 | 10 | 12-Mar-23 | 22-Mar-23 | WPIELC098 | LBR | Labor | 2725 | FALSE | NO
WPIELC051 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Switchboards Installation | 3 | 3 | 12-Sep-23 | 15-Sep-23 | WPIELC050 | LBR | Labor | 1622 | FALSE | NO
WPIELC087 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | 120kW Solar Panel Setup | 9 | 9 | 12-Sep-23 | 21-Sep-23 | WPIELC086 | LBR | Labor | 3901 | FALSE | NO
WPIELC074 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Lighting System Installation | 3 | 3 | 13-Mar-24 | 16-Mar-24 | WPIELC073 | LBR | Labor | 4011 | FALSE | NO
WPIELC040 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Electrical Commissioning | 5 | 5 | 14-Jan-24 | 19-Jan-24 | WPIELC039 | LBR | Labor | 6342 | FALSE | NO
WPIELC041 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Cable Tray Installation | 10 | 10 | 14-Jun-24 | 24-Jun-24 | WPIELC040 | LBR | Labor | 9432 | FALSE | NO
WPIELC033 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Cable Tray Installation | 9 | 9 | 14-May-23 | 23-May-23 | WPIELC032 | LBR | Labor | 9887 | FALSE | NO
WPIELC005 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Automation Wiring | 8 | 8 | 15-Aug-24 | 23-Aug-24 | WPIELC004 | LBR | Labor | 6552 | FALSE | NO
WPIELC055 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | 120kW Solar Panel Setup | 7 | 7 | 15-Jan-24 | 22-Jan-24 | WPIELC054 | LBR | Labor | 9587 | FALSE | NO
WPIELC032 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Electrical Commissioning | 8 | 8 | 15-Jul-23 | 23-Jul-23 | WPIELC031 | LBR | Labor | 5098 | FALSE | NO
WPIELC049 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Cable Tray Installation | 4 | 4 | 15-Jul-23 | 19-Jul-23 | WPIELC048 | LBR | Labor | 9140 | FALSE | NO
WPIELC010 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Lighting System Installation | 8 | 8 | 15-Nov-23 | 23-Nov-23 | WPIELC009 | LBR | Labor | 4251 | FALSE | NO
WPIELC020 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Power Panel Setup | 10 | 10 | 16-Dec-23 | 26-Dec-23 | WPIELC019 | LBR | Labor | 843 | FALSE | NO
WPIELC081 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Cable Tray Installation | 9 | 9 | 17-Jan-24 | 26-Jan-24 | WPIELC080 | LBR | Labor | 8282 | FALSE | NO
WPIELC068 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Power Panel Setup | 3 | 3 | 17-Nov-23 | 20-Nov-23 | WPIELC067 | LBR | Labor | 6916 | FALSE | NO
WPIELC052 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Power Panel Setup | 6 | 6 | 18-Apr-23 | 24-Apr-23 | WPIELC051 | LBR | Labor | 2130 | FALSE | NO
WPIELC036 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Power Panel Setup | 9 | 9 | 18-Jul-24 | 27-Jul-24 | WPIELC035 | LBR | Labor | 580 | FALSE | NO
WPIELC063 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | 120kW Solar Panel Setup | 3 | 3 | 19-Aug-23 | 22-Aug-23 | WPIELC062 | LBR | Labor | 5779 | FALSE | NO
WPIELC091 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Switchboards Installation | 4 | 4 | 19-Feb-23 | 23-Feb-23 | WPIELC090 | LBR | Labor | 5513 | FALSE | NO
WPIELC057 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Cable Tray Installation | 10 | 10 | 19-Feb-24 | 29-Feb-24 | WPIELC056 | LBR | Labor | 8383 | FALSE | NO
WPIELC003 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Switchboards Installation | 5 | 5 | 19-Jan-24 | 24-Jan-24 | WPIELC002 | LBR | Labor | 1294 | FALSE | NO
WPIELC050 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Lighting System Installation | 9 | 9 | 19-Jan-24 | 28-Jan-24 | WPIELC049 | LBR | Labor | 1105 | FALSE | NO
WPIELC085 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Automation Wiring | 7 | 7 | 19-Jan-24 | 26-Jan-24 | WPIELC084 | LBR | Labor | 5764 | FALSE | NO
WPIELC034 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Lighting System Installation | 3 | 3 | 19-Jul-23 | 22-Jul-23 | WPIELC033 | LBR | Labor | 3868 | FALSE | NO
WPIELC029 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Automation Wiring | 3 | 3 | 19-Jul-24 | 22-Jul-24 | WPIELC028 | LBR | Labor | 3681 | FALSE | NO
WPIELC092 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Power Panel Setup | 9 | 9 | 19-Jul-24 | 28-Jul-24 | WPIELC091 | LBR | Labor | 4266 | FALSE | NO
WPIELC027 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Switchboards Installation | 4 | 4 | 20-Apr-23 | 24-Apr-23 | WPIELC026 | LBR | Labor | 5131 | FALSE | NO
WPIELC014 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install CCTV System | 7 | 7 | 20-Aug-23 | 27-Aug-23 | WPIELC013 | LBR | Labor | 7660 | FALSE | NO
WPIELC079 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | 120kW Solar Panel Setup | 7 | 7 | 22-Aug-24 | 29-Aug-24 | WPIELC078 | LBR | Labor | 5564 | FALSE | NO
WPIELC098 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Lighting System Installation | 5 | 5 | 22-Jan-24 | 27-Jan-24 | WPIELC097 | LBR | Labor | 3652 | FALSE | NO
WPIELC008 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Electrical Commissioning | 3 | 3 | 22-Jul-24 | 25-Jul-24 | WPIELC007 | LBR | Labor | 1382 | FALSE | NO
WPIELC072 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Electrical Commissioning | 6 | 6 | 23-Apr-23 | 29-Apr-23 | WPIELC071 | LBR | Labor | 7140 | FALSE | NO
WPIELC023 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | 120kW Solar Panel Setup | 8 | 8 | 23-Jun-23 | 01-Jul-23 | WPIELC022 | LBR | Labor | 8172 | FALSE | NO
WPIELC044 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Power Panel Setup | 5 | 5 | 23-May-24 | 28-May-24 | WPIELC043 | LBR | Labor | 535 | FALSE | NO
WPIELC001 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Cable Tray Installation | 10 | 10 | 23-Sep-23 | 03-Oct-23 |  | LBR | Labor | 9694 | FALSE | NO
WPIELC046 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install CCTV System | 10 | 10 | 24-Aug-23 | 03-Sep-23 | WPIELC045 | LBR | Labor | 7847 | FALSE | NO
WPIELC100 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Power Panel Setup | 7 | 7 | 24-Jan-24 | 31-Jan-24 | WPIELC099 | LBR | Labor | 8220 | FALSE | NO
WPIELC026 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Lighting System Installation | 10 | 10 | 24-Nov-23 | 04-Dec-23 | WPIELC025 | LBR | Labor | 2219 | FALSE | NO
WPIELC096 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Electrical Commissioning | 8 | 8 | 24-Oct-23 | 01-Nov-23 | WPIELC095 | LBR | Labor | 4618 | FALSE | NO
WPIELC025 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Cable Tray Installation | 10 | 10 | 24-Sep-23 | 04-Oct-23 | WPIELC024 | LBR | Labor | 5283 | FALSE | NO
WPIELC021 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Automation Wiring | 4 | 4 | 25-Mar-24 | 29-Mar-24 | WPIELC020 | LBR | Labor | 5946 | FALSE | NO
WPIELC058 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Lighting System Installation | 10 | 10 | 25-May-24 | 04-Jun-24 | WPIELC057 | LBR | Labor | 7736 | FALSE | NO
WPIELC006 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install CCTV System | 9 | 9 | 26-Dec-23 | 04-Jan-24 | WPIELC005 | LBR | Labor | 5716 | FALSE | NO
WPIELC088 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Electrical Commissioning | 8 | 8 | 26-Feb-24 | 05-Mar-24 | WPIELC087 | LBR | Labor | 6847 | FALSE | NO
WPIELC082 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Lighting System Installation | 3 | 3 | 26-Jan-24 | 29-Jan-24 | WPIELC081 | LBR | Labor | 6230 | FALSE | NO
WPIELC012 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Power Panel Setup | 9 | 9 | 26-May-24 | 04-Jun-24 | WPIELC011 | LBR | Labor | 6663 | FALSE | NO
WPIELC013 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Automation Wiring | 4 | 4 | 26-Nov-23 | 30-Nov-23 | WPIELC012 | LBR | Labor | 9213 | FALSE | NO
WPIELC028 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Power Panel Setup | 10 | 10 | 27-Feb-23 | 09-Mar-23 | WPIELC027 | LBR | Labor | 7539 | FALSE | NO
WPIELC007 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | 120kW Solar Panel Setup | 6 | 6 | 27-Mar-24 | 02-Apr-24 | WPIELC006 | LBR | Labor | 4265 | FALSE | NO
WPIELC018 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Lighting System Installation | 6 | 6 | 27-Mar-24 | 02-Apr-24 | WPIELC017 | LBR | Labor | 4006 | FALSE | NO
WPIELC053 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Automation Wiring | 7 | 7 | 27-May-23 | 03-Jun-23 | WPIELC052 | LBR | Labor | 5986 | FALSE | NO
WPIELC060 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Power Panel Setup | 4 | 4 | 27-Nov-23 | 01-Dec-23 | WPIELC059 | LBR | Labor | 3581 | FALSE | NO
WPIELC062 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install CCTV System | 6 | 6 | 27-Nov-23 | 03-Dec-23 | WPIELC061 | LBR | Labor | 1565 | FALSE | NO
WPIELC031 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | 120kW Solar Panel Setup | 4 | 4 | 28-Apr-23 | 02-May-23 | WPIELC030 | LBR | Labor | 574 | FALSE | NO
WPIELC064 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Electrical Commissioning | 6 | 6 | 28-Jul-23 | 03-Aug-23 | WPIELC063 | LBR | Labor | 5642 | FALSE | NO
WPIELC078 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install CCTV System | 7 | 7 | 28-Mar-23 | 04-Apr-23 | WPIELC077 | LBR | Labor | 6962 | FALSE | NO
WPIELC047 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | 120kW Solar Panel Setup | 4 | 4 | 28-Mar-24 | 01-Apr-24 | WPIELC046 | LBR | Labor | 1304 | FALSE | NO
WPIELC066 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Lighting System Installation | 7 | 7 | 28-May-24 | 04-Jun-24 | WPIELC065 | LBR | Labor | 5600 | FALSE | NO
WPIELC061 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Automation Wiring | 7 | 7 | 28-Sep-23 | 05-Oct-23 | WPIELC060 | LBR | Labor | 9501 | FALSE | NO
WPIELC054 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install CCTV System | 7 | 7 | 29-Dec-23 | 05-Jan-24 | WPIELC053 | LBR | Labor | 9302 | FALSE | NO
WPIELC075 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Switchboards Installation | 5 | 5 | 29-Mar-24 | 03-Apr-24 | WPIELC074 | LBR | Labor | 8464 | FALSE | NO
WPIELC083 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Switchboards Installation | 6 | 6 | 29-Mar-24 | 04-Apr-24 | WPIELC082 | LBR | Labor | 1024 | FALSE | NO
WPIELC030 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install CCTV System | 9 | 9 | 29-May-23 | 07-Jun-23 | WPIELC029 | LBR | Labor | 1614 | FALSE | NO
WPIELC089 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Cable Tray Installation | 4 | 4 | 29-May-23 | 02-Jun-23 | WPIELC088 | LBR | Labor | 9971 | FALSE | NO
WPIELC035 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Switchboards Installation | 3 | 3 | 30-Sep-23 | 03-Oct-23 | WPIELC034 | LBR | Labor | 1959 | FALSE | NO
WPIELC039 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | 120kW Solar Panel Setup | 6 | 6 | 31-Dec-23 | 06-Jan-24 | WPIELC038 | LBR | Labor | 3890 | FALSE | NO
WPIELC037 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Automation Wiring | 5 | 5 | 31-Mar-23 | 05-Apr-23 | WPIELC036 | LBR | Labor | 2086 | FALSE | NO
WPIFIN030 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Final Civil Touch-up | 10 | 10 | 01-Aug-23 | 11-Aug-23 | WPIFIN029 | LBR | Labor | 7395 | FALSE | NO
WPIFIN041 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Internal Wall Construction | 8 | 8 | 01-Dec-23 | 09-Dec-23 | WPIFIN040 | LBR | Labor | 3589 | FALSE | NO
WPIFIN071 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Internal Wall Construction | 6 | 6 | 01-Jul-23 | 07-Jul-23 | WPIFIN070 | LBR | Labor | 9840 | FALSE | NO
WPIFIN032 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Plastering – Ground Floor | 4 | 4 | 01-Jul-24 | 05-Jul-24 | WPIFIN031 | LBR | Labor | 7225 | FALSE | NO
WPIFIN091 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Internal Wall Construction | 9 | 9 | 01-Mar-24 | 10-Mar-24 | WPIFIN090 | LBR | Labor | 3432 | FALSE | NO
WPIFIN077 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Doors & Windows Installation | 3 | 3 | 01-Nov-23 | 04-Nov-23 | WPIFIN076 | LBR | Labor | 5910 | FALSE | NO
WPIFIN024 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Floor Tiling – Ground Floor | 9 | 9 | 02-May-23 | 11-May-23 | WPIFIN023 | LBR | Labor | 1421 | FALSE | NO
WPIFIN017 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Doors & Windows Installation | 4 | 4 | 02-May-24 | 06-May-24 | WPIFIN016 | LBR | Labor | 7807 | FALSE | NO
WPIFIN013 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Plastering – 1st Floor | 8 | 8 | 02-Oct-23 | 10-Oct-23 | WPIFIN012 | LBR | Labor | 8902 | FALSE | NO
WPIFIN063 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Plastering – 1st Floor | 8 | 8 | 02-Sep-23 | 10-Sep-23 | WPIFIN062 | LBR | Labor | 588 | FALSE | NO
WPIFIN093 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Plastering – 1st Floor | 3 | 3 | 03-Jan-23 | 06-Jan-23 | WPIFIN092 | LBR | Labor | 2438 | FALSE | NO
WPIFIN081 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Internal Wall Construction | 4 | 4 | 04-Dec-23 | 08-Dec-23 | WPIFIN080 | LBR | Labor | 1541 | FALSE | NO
WPIFIN004 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Floor Tiling – Ground Floor | 8 | 8 | 04-Feb-23 | 12-Feb-23 | WPIFIN003 | LBR | Labor | 7697 | FALSE | NO
WPIFIN016 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Paint & Finish – All Floors | 6 | 6 | 04-Jul-24 | 10-Jul-24 | WPIFIN015 | LBR | Labor | 8442 | FALSE | NO
WPIFIN044 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Floor Tiling – Ground Floor | 9 | 9 | 04-Jun-24 | 13-Jun-24 | WPIFIN043 | LBR | Labor | 4982 | FALSE | NO
WPIFIN009 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Sanitary Fixes – All Floors | 4 | 4 | 05-Dec-23 | 09-Dec-23 | WPIFIN008 | LBR | Labor | 6085 | FALSE | NO
WPIFIN054 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Floor Tiling – Ground Floor | 10 | 10 | 05-May-24 | 15-May-24 | WPIFIN053 | LBR | Labor | 8863 | FALSE | NO
WPIFIN018 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Plumbing – Ground Floor | 8 | 8 | 06-Apr-24 | 14-Apr-24 | WPIFIN017 | LBR | Labor | 7314 | FALSE | NO
WPIFIN010 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Final Civil Touch-up | 3 | 3 | 06-Feb-24 | 09-Feb-24 | WPIFIN009 | LBR | Labor | 793 | FALSE | NO
WPIFIN056 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Paint & Finish – All Floors | 6 | 6 | 07-Nov-23 | 13-Nov-23 | WPIFIN055 | LBR | Labor | 3888 | FALSE | NO
WPIFIN079 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Sanitary Fixes – All Floors | 10 | 10 | 08-Apr-23 | 18-Apr-23 | WPIFIN078 | LBR | Labor | 6626 | FALSE | NO
WPIFIN011 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Internal Wall Construction | 6 | 6 | 08-Jan-23 | 14-Jan-23 | WPIFIN010 | LBR | Labor | 6439 | FALSE | NO
WPIFIN082 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Plastering – Ground Floor | 9 | 9 | 08-Jul-24 | 17-Jul-24 | WPIFIN081 | LBR | Labor | 7914 | FALSE | NO
WPIFIN099 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Sanitary Fixes – All Floors | 5 | 5 | 08-Mar-23 | 13-Mar-23 | WPIFIN098 | LBR | Labor | 9477 | FALSE | NO
WPIFIN060 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Final Civil Touch-up | 6 | 6 | 08-Nov-23 | 14-Nov-23 | WPIFIN059 | LBR | Labor | 8973 | FALSE | NO
WPIFIN007 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Doors & Windows Installation | 9 | 9 | 09-Apr-23 | 18-Apr-23 | WPIFIN006 | LBR | Labor | 8818 | FALSE | NO
WPIFIN008 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Plumbing – Ground Floor | 7 | 7 | 09-Jul-24 | 16-Jul-24 | WPIFIN007 | LBR | Labor | 1423 | FALSE | NO
WPIFIN048 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Plumbing – Ground Floor | 6 | 6 | 09-May-23 | 15-May-23 | WPIFIN047 | LBR | Labor | 7994 | FALSE | NO
WPIFIN026 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Paint & Finish – All Floors | 4 | 4 | 10-Feb-23 | 14-Feb-23 | WPIFIN025 | LBR | Labor | 2317 | FALSE | NO
WPIFIN086 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Paint & Finish – All Floors | 8 | 8 | 10-Jun-24 | 18-Jun-24 | WPIFIN085 | LBR | Labor | 6180 | FALSE | NO
WPIFIN027 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Doors & Windows Installation | 8 | 8 | 11-Apr-24 | 19-Apr-24 | WPIFIN026 | LBR | Labor | 9504 | FALSE | NO
WPIFIN074 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Floor Tiling – Ground Floor | 6 | 6 | 11-Feb-24 | 17-Feb-24 | WPIFIN073 | LBR | Labor | 3686 | FALSE | NO
WPIFIN014 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Floor Tiling – Ground Floor | 4 | 4 | 11-Jan-24 | 15-Jan-24 | WPIFIN013 | LBR | Labor | 2088 | FALSE | NO
WPIFIN073 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Plastering – 1st Floor | 6 | 6 | 11-Jul-23 | 17-Jul-23 | WPIFIN072 | LBR | Labor | 5511 | FALSE | NO
WPIFIN087 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Doors & Windows Installation | 9 | 9 | 11-Nov-23 | 20-Nov-23 | WPIFIN086 | LBR | Labor | 2662 | FALSE | NO
WPIFIN067 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Doors & Windows Installation | 3 | 3 | 11-Sep-23 | 14-Sep-23 | WPIFIN066 | LBR | Labor | 9409 | FALSE | NO
WPIFIN022 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Plastering – Ground Floor | 4 | 4 | 12-May-23 | 16-May-23 | WPIFIN021 | LBR | Labor | 2473 | FALSE | NO
WPIFIN037 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Doors & Windows Installation | 7 | 7 | 12-May-23 | 19-May-23 | WPIFIN036 | LBR | Labor | 6981 | FALSE | NO
WPIFIN012 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Plastering – Ground Floor | 3 | 3 | 12-Nov-23 | 15-Nov-23 | WPIFIN011 | LBR | Labor | 3161 | FALSE | NO
WPIFIN025 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Floor Tiling – 1st Floor | 3 | 3 | 13-Dec-23 | 16-Dec-23 | WPIFIN024 | LBR | Labor | 6665 | FALSE | NO
WPIFIN069 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Sanitary Fixes – All Floors | 4 | 4 | 13-Jan-23 | 17-Jan-23 | WPIFIN068 | LBR | Labor | 6963 | FALSE | NO
WPIFIN096 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Paint & Finish – All Floors | 6 | 6 | 13-Jan-24 | 19-Jan-24 | WPIFIN095 | LBR | Labor | 2504 | FALSE | NO
WPIFIN090 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Final Civil Touch-up | 4 | 4 | 13-May-23 | 17-May-23 | WPIFIN089 | LBR | Labor | 2020 | FALSE | NO
WPIFIN045 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Floor Tiling – 1st Floor | 9 | 9 | 14-Dec-23 | 23-Dec-23 | WPIFIN044 | LBR | Labor | 1540 | FALSE | NO
WPIFIN068 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Plumbing – Ground Floor | 3 | 3 | 14-Oct-23 | 17-Oct-23 | WPIFIN067 | LBR | Labor | 3184 | FALSE | NO
WPIFIN085 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Floor Tiling – 1st Floor | 3 | 3 | 15-Apr-23 | 18-Apr-23 | WPIFIN084 | LBR | Labor | 6573 | FALSE | NO
WPIFIN070 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Final Civil Touch-up | 4 | 4 | 15-Jan-24 | 19-Jan-24 | WPIFIN069 | LBR | Labor | 8995 | FALSE | NO
WPIFIN078 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Plumbing – Ground Floor | 3 | 3 | 15-May-23 | 18-May-23 | WPIFIN077 | LBR | Labor | 7826 | FALSE | NO
WPIFIN021 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Internal Wall Construction | 10 | 10 | 16-Apr-23 | 26-Apr-23 | WPIFIN020 | LBR | Labor | 4441 | FALSE | NO
WPIFIN049 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Sanitary Fixes – All Floors | 4 | 4 | 16-Jul-23 | 20-Jul-23 | WPIFIN048 | LBR | Labor | 6543 | FALSE | NO
WPIFIN062 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Plastering – Ground Floor | 8 | 8 | 16-Jun-23 | 24-Jun-23 | WPIFIN061 | LBR | Labor | 4729 | FALSE | NO
WPIFIN092 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Plastering – Ground Floor | 4 | 4 | 16-Jun-23 | 20-Jun-23 | WPIFIN091 | LBR | Labor | 4901 | FALSE | NO
WPIFIN002 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Plastering – Ground Floor | 7 | 7 | 16-Nov-23 | 23-Nov-23 | WPIFIN001 | LBR | Labor | 5466 | FALSE | NO
WPIFIN019 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Sanitary Fixes – All Floors | 3 | 3 | 16-Nov-23 | 19-Nov-23 | WPIFIN018 | LBR | Labor | 9052 | FALSE | NO
WPIFIN066 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Paint & Finish – All Floors | 5 | 5 | 17-Feb-24 | 22-Feb-24 | WPIFIN065 | LBR | Labor | 3640 | FALSE | NO
WPIFIN028 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Plumbing – Ground Floor | 9 | 9 | 18-Jul-24 | 27-Jul-24 | WPIFIN027 | LBR | Labor | 7047 | FALSE | NO
WPIFIN052 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Plastering – Ground Floor | 10 | 10 | 18-Nov-23 | 28-Nov-23 | WPIFIN051 | LBR | Labor | 6050 | FALSE | NO
WPIFIN064 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Floor Tiling – Ground Floor | 9 | 9 | 19-Jul-23 | 28-Jul-23 | WPIFIN063 | LBR | Labor | 4379 | FALSE | NO
WPIFIN053 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Plastering – 1st Floor | 5 | 5 | 19-Jun-24 | 24-Jun-24 | WPIFIN052 | LBR | Labor | 3172 | FALSE | NO
WPIFIN061 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Internal Wall Construction | 7 | 7 | 19-Sep-23 | 26-Sep-23 | WPIFIN060 | LBR | Labor | 3167 | FALSE | NO
WPIFIN043 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Plastering – 1st Floor | 8 | 8 | 20-Feb-23 | 28-Feb-23 | WPIFIN042 | LBR | Labor | 6246 | FALSE | NO
WPIFIN020 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Final Civil Touch-up | 5 | 5 | 20-Jul-24 | 25-Jul-24 | WPIFIN019 | LBR | Labor | 1204 | FALSE | NO
WPIFIN036 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Paint & Finish – All Floors | 7 | 7 | 20-Nov-23 | 27-Nov-23 | WPIFIN035 | LBR | Labor | 5654 | FALSE | NO
WPIFIN094 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Floor Tiling – Ground Floor | 5 | 5 | 20-Nov-23 | 25-Nov-23 | WPIFIN093 | LBR | Labor | 1770 | FALSE | NO
WPIFIN058 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Plumbing – Ground Floor | 9 | 9 | 21-Apr-23 | 30-Apr-23 | WPIFIN057 | LBR | Labor | 2502 | FALSE | NO
WPIFIN050 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Final Civil Touch-up | 4 | 4 | 21-Jan-24 | 25-Jan-24 | WPIFIN049 | LBR | Labor | 8260 | FALSE | NO
WPIFIN042 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Plastering – Ground Floor | 10 | 10 | 21-Jun-23 | 01-Jul-23 | WPIFIN041 | LBR | Labor | 4772 | FALSE | NO
WPIFIN001 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Internal Wall Construction | 9 | 9 | 22-Apr-24 | 01-May-24 |  | LBR | Labor | 8372 | FALSE | NO
WPIFIN098 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Plumbing – Ground Floor | 9 | 9 | 22-Feb-23 | 03-Mar-23 | WPIFIN097 | LBR | Labor | 705 | FALSE | NO
WPIFIN035 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Floor Tiling – 1st Floor | 9 | 9 | 22-Feb-24 | 02-Mar-24 | WPIFIN034 | LBR | Labor | 7120 | FALSE | NO
WPIFIN005 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Floor Tiling – 1st Floor | 5 | 5 | 22-Jan-23 | 27-Jan-23 | WPIFIN004 | LBR | Labor | 6181 | FALSE | NO
WPIFIN031 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Internal Wall Construction | 5 | 5 | 22-Jul-24 | 27-Jul-24 | WPIFIN030 | LBR | Labor | 9336 | FALSE | NO
WPIFIN072 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Plastering – Ground Floor | 10 | 10 | 22-Jun-23 | 02-Jul-23 | WPIFIN071 | LBR | Labor | 8125 | FALSE | NO
WPIFIN100 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Final Civil Touch-up | 9 | 9 | 23-Apr-23 | 02-May-23 | WPIFIN099 | LBR | Labor | 1619 | FALSE | NO
WPIFIN015 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Floor Tiling – 1st Floor | 9 | 9 | 23-Aug-24 | 01-Sep-24 | WPIFIN014 | LBR | Labor | 9551 | FALSE | NO
WPIFIN039 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Sanitary Fixes – All Floors | 5 | 5 | 23-Dec-23 | 28-Dec-23 | WPIFIN038 | LBR | Labor | 4231 | FALSE | NO
WPIFIN046 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Paint & Finish – All Floors | 4 | 4 | 23-Feb-24 | 27-Feb-24 | WPIFIN045 | LBR | Labor | 5162 | FALSE | NO
WPIFIN003 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Plastering – 1st Floor | 5 | 5 | 23-Jan-23 | 28-Jan-23 | WPIFIN002 | LBR | Labor | 8654 | FALSE | NO
WPIFIN034 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Floor Tiling – Ground Floor | 8 | 8 | 23-Jan-23 | 31-Jan-23 | WPIFIN033 | LBR | Labor | 8928 | FALSE | NO
WPIFIN080 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Final Civil Touch-up | 8 | 8 | 23-Jun-23 | 01-Jul-23 | WPIFIN079 | LBR | Labor | 7484 | FALSE | NO
WPIFIN095 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Floor Tiling – 1st Floor | 4 | 4 | 23-May-23 | 27-May-23 | WPIFIN094 | LBR | Labor | 4951 | FALSE | NO
WPIFIN065 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Floor Tiling – 1st Floor | 4 | 4 | 23-Sep-23 | 27-Sep-23 | WPIFIN064 | LBR | Labor | 4708 | FALSE | NO
WPIFIN059 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Sanitary Fixes – All Floors | 9 | 9 | 24-Feb-24 | 04-Mar-24 | WPIFIN058 | LBR | Labor | 7425 | FALSE | NO
WPIFIN051 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Internal Wall Construction | 8 | 8 | 24-Jun-24 | 02-Jul-24 | WPIFIN050 | LBR | Labor | 5079 | FALSE | NO
WPIFIN057 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Doors & Windows Installation | 7 | 7 | 24-May-23 | 31-May-23 | WPIFIN056 | LBR | Labor | 1691 | FALSE | NO
WPIFIN023 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Plastering – 1st Floor | 6 | 6 | 24-May-24 | 30-May-24 | WPIFIN022 | LBR | Labor | 5200 | FALSE | NO
WPIFIN038 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Plumbing – Ground Floor | 8 | 8 | 25-May-24 | 02-Jun-24 | WPIFIN037 | LBR | Labor | 3618 | FALSE | NO
WPIFIN097 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Doors & Windows Installation | 5 | 5 | 26-Dec-23 | 31-Dec-23 | WPIFIN096 | LBR | Labor | 8010 | FALSE | NO
WPIFIN084 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Floor Tiling – Ground Floor | 4 | 4 | 26-Feb-23 | 02-Mar-23 | WPIFIN083 | LBR | Labor | 1546 | FALSE | NO
WPIFIN076 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Paint & Finish – All Floors | 3 | 3 | 26-Jul-24 | 29-Jul-24 | WPIFIN075 | LBR | Labor | 3057 | FALSE | NO
WPIFIN033 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Plastering – 1st Floor | 9 | 9 | 27-Aug-23 | 05-Sep-23 | WPIFIN032 | LBR | Labor | 8827 | FALSE | NO
WPIFIN047 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Doors & Windows Installation | 8 | 8 | 27-May-23 | 04-Jun-23 | WPIFIN046 | LBR | Labor | 9632 | FALSE | NO
WPIFIN040 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Final Civil Touch-up | 3 | 3 | 28-Feb-23 | 03-Mar-23 | WPIFIN039 | LBR | Labor | 4089 | FALSE | NO
WPIFIN075 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Floor Tiling – 1st Floor | 9 | 9 | 28-Jul-23 | 06-Aug-23 | WPIFIN074 | LBR | Labor | 1473 | FALSE | NO
WPIFIN088 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Plumbing – Ground Floor | 4 | 4 | 28-Jun-24 | 02-Jul-24 | WPIFIN087 | LBR | Labor | 8836 | FALSE | NO
WPIFIN089 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Sanitary Fixes – All Floors | 6 | 6 | 29-Jan-24 | 04-Feb-24 | WPIFIN088 | LBR | Labor | 4575 | FALSE | NO
WPIFIN083 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Plastering – 1st Floor | 10 | 10 | 29-Jun-23 | 09-Jul-23 | WPIFIN082 | LBR | Labor | 6529 | FALSE | NO
WPIFIN006 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Paint & Finish – All Floors | 5 | 5 | 30-Jul-23 | 04-Aug-23 | WPIFIN005 | LBR | Labor | 2835 | FALSE | NO
WPIFIN055 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Floor Tiling – 1st Floor | 8 | 8 | 31-Aug-23 | 08-Sep-23 | WPIFIN054 | LBR | Labor | 7250 | FALSE | NO
WPIFIN029 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Sanitary Fixes – All Floors | 8 | 8 | 31-Mar-24 | 08-Apr-24 | WPIFIN028 | LBR | Labor | 3695 | FALSE | NO
WPIMACH017 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | BOQ Finalization | 10 | 10 | 01-Aug-24 | 11-Aug-24 | WPIMACH016 | LBR | Labor | 9519 | FALSE | NO
WPIMACH029 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Printing Machine Setup | 8 | 8 | 01-Dec-23 | 09-Dec-23 | WPIMACH028 | LBR | Labor | 3664 | FALSE | NO
WPIMACH109 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Printing Machine Setup | 4 | 4 | 01-Jan-24 | 05-Jan-24 | WPIMACH108 | LBR | Labor | 6919 | FALSE | NO
WPIMACH080 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Dry Run Testing | 6 | 6 | 02-Aug-23 | 08-Aug-23 | WPIMACH079 | LBR | Labor | 5743 | FALSE | NO
WPIMACH042 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Vendor Selection | 3 | 3 | 02-Feb-23 | 05-Feb-23 | WPIMACH041 | LBR | Labor | 3779 | FALSE | NO
WPIMACH015 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Machine Calibration | 10 | 10 | 02-Nov-23 | 12-Nov-23 | WPIMACH014 | LBR | Labor | 3503 | FALSE | NO
WPIMACH024 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Dry Run Testing | 9 | 9 | 03-Dec-23 | 12-Dec-23 | WPIMACH023 | LBR | Labor | 9574 | FALSE | NO
WPIMACH108 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Thermoformer Setup | 9 | 9 | 03-Feb-23 | 12-Feb-23 | WPIMACH107 | LBR | Labor | 5066 | FALSE | NO
WPIMACH096 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Dry Run Testing | 7 | 7 | 03-Feb-24 | 10-Feb-24 | WPIMACH095 | LBR | Labor | 4687 | FALSE | NO
WPIMACH102 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Robotic Arm Integration | 10 | 10 | 03-Jul-24 | 13-Jul-24 | WPIMACH101 | LBR | Labor | 4996 | FALSE | NO
WPIMACH013 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Printing Machine Setup | 5 | 5 | 03-Mar-24 | 08-Mar-24 | WPIMACH012 | LBR | Labor | 7481 | FALSE | NO
WPIMACH094 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Robotic Arm Integration | 4 | 4 | 03-Nov-23 | 07-Nov-23 | WPIMACH093 | LBR | Labor | 3125 | FALSE | NO
WPIMACH034 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Vendor Selection | 9 | 9 | 03-Sep-23 | 12-Sep-23 | WPIMACH033 | LBR | Labor | 4143 | FALSE | NO
WPIMACH123 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Extruder Installation | 9 | 9 | 04-Apr-24 | 13-Apr-24 | WPIMACH122 | LBR | Labor | 5156 | FALSE | NO
WPIMACH053 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Printing Machine Setup | 9 | 9 | 04-Dec-23 | 13-Dec-23 | WPIMACH052 | LBR | Labor | 9823 | FALSE | NO
WPIMACH126 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Robotic Arm Integration | 7 | 7 | 04-Feb-24 | 11-Feb-24 | WPIMACH125 | LBR | Labor | 8755 | FALSE | NO
WPIMACH022 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Robotic Arm Integration | 9 | 9 | 04-May-23 | 13-May-23 | WPIMACH021 | LBR | Labor | 9712 | FALSE | NO
WPIMACH089 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | BOQ Finalization | 7 | 7 | 04-May-24 | 11-May-24 | WPIMACH088 | LBR | Labor | 3605 | FALSE | NO
WPIMACH119 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Machine Calibration | 9 | 9 | 05-Aug-24 | 14-Aug-24 | WPIMACH118 | LBR | Labor | 1713 | FALSE | NO
WPIMACH101 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Printing Machine Setup | 8 | 8 | 05-Feb-23 | 13-Feb-23 | WPIMACH100 | LBR | Labor | 5078 | FALSE | NO
WPIMACH077 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Printing Machine Setup | 7 | 7 | 05-Feb-24 | 12-Feb-24 | WPIMACH076 | LBR | Labor | 3022 | FALSE | NO
WPIMACH041 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | BOQ Finalization | 6 | 6 | 05-Jan-23 | 11-Jan-23 | WPIMACH040 | LBR | Labor | 4023 | FALSE | NO
WPIMACH036 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Thermoformer Setup | 10 | 10 | 05-Jul-24 | 15-Jul-24 | WPIMACH035 | LBR | Labor | 5331 | FALSE | NO
WPIMACH118 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Robotic Arm Integration | 5 | 5 | 05-Jun-23 | 10-Jun-23 | WPIMACH117 | LBR | Labor | 4517 | FALSE | NO
WPIMACH127 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Machine Calibration | 10 | 10 | 06-Aug-24 | 16-Aug-24 | WPIMACH126 | LBR | Labor | 9710 | FALSE | NO
WPIMACH044 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Thermoformer Setup | 9 | 9 | 06-Jan-23 | 15-Jan-23 | WPIMACH043 | LBR | Labor | 7460 | FALSE | NO
WPIMACH051 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Extruder Installation | 8 | 8 | 06-May-23 | 14-May-23 | WPIMACH050 | LBR | Labor | 1458 | FALSE | NO
WPIMACH114 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Vendor Selection | 3 | 3 | 06-May-24 | 09-May-24 | WPIMACH113 | LBR | Labor | 2130 | FALSE | NO
WPIMACH003 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Extruder Installation | 7 | 7 | 07-Apr-24 | 14-Apr-24 | WPIMACH002 | LBR | Labor | 651 | FALSE | NO
WPIMACH040 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Dry Run Testing | 4 | 4 | 07-Aug-23 | 11-Aug-23 | WPIMACH039 | LBR | Labor | 1522 | FALSE | NO
WPIMACH062 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Robotic Arm Integration | 8 | 8 | 07-Aug-23 | 15-Aug-23 | WPIMACH061 | LBR | Labor | 9148 | FALSE | NO
WPIMACH047 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Machine Calibration | 5 | 5 | 07-Feb-23 | 12-Feb-23 | WPIMACH046 | LBR | Labor | 9691 | FALSE | NO
WPIMACH065 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | BOQ Finalization | 7 | 7 | 07-Mar-24 | 14-Mar-24 | WPIMACH064 | LBR | Labor | 642 | FALSE | NO
WPIMACH031 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Machine Calibration | 7 | 7 | 07-Nov-23 | 14-Nov-23 | WPIMACH030 | LBR | Labor | 2674 | FALSE | NO
WPIMACH038 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Robotic Arm Integration | 7 | 7 | 08-Aug-23 | 15-Aug-23 | WPIMACH037 | LBR | Labor | 1799 | FALSE | NO
WPIMACH112 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Dry Run Testing | 5 | 5 | 08-Mar-24 | 13-Mar-24 | WPIMACH111 | LBR | Labor | 6424 | FALSE | NO
WPIMACH120 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Dry Run Testing | 6 | 6 | 08-Oct-23 | 14-Oct-23 | WPIMACH119 | LBR | Labor | 7803 | FALSE | NO
WPIMACH048 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Dry Run Testing | 8 | 8 | 08-Sep-23 | 16-Sep-23 | WPIMACH047 | LBR | Labor | 1565 | FALSE | NO
WPIMACH020 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Thermoformer Setup | 4 | 4 | 09-Feb-24 | 13-Feb-24 | WPIMACH019 | LBR | Labor | 3435 | FALSE | NO
WPIMACH067 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Extruder Installation | 7 | 7 | 09-Feb-24 | 16-Feb-24 | WPIMACH066 | LBR | Labor | 3792 | FALSE | NO
WPIMACH103 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Machine Calibration | 7 | 7 | 09-Jan-23 | 16-Jan-23 | WPIMACH102 | LBR | Labor | 9479 | FALSE | NO
WPIMACH056 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Dry Run Testing | 6 | 6 | 09-Jun-23 | 15-Jun-23 | WPIMACH055 | LBR | Labor | 6706 | FALSE | NO
WPIMACH004 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Thermoformer Setup | 4 | 4 | 09-May-23 | 13-May-23 | WPIMACH003 | LBR | Labor | 4140 | FALSE | NO
WPIMACH072 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Dry Run Testing | 6 | 6 | 10-Aug-24 | 16-Aug-24 | WPIMACH071 | LBR | Labor | 5391 | FALSE | NO
WPIMACH007 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Machine Calibration | 6 | 6 | 10-Mar-24 | 16-Mar-24 | WPIMACH006 | LBR | Labor | 4052 | FALSE | NO
WPIMACH106 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Vendor Selection | 3 | 3 | 11-Jan-23 | 14-Jan-23 | WPIMACH105 | LBR | Labor | 9173 | FALSE | NO
WPIMACH037 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Printing Machine Setup | 8 | 8 | 11-Jul-23 | 19-Jul-23 | WPIMACH036 | LBR | Labor | 6282 | FALSE | NO
WPIMACH014 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Robotic Arm Integration | 5 | 5 | 11-Jul-24 | 16-Jul-24 | WPIMACH013 | LBR | Labor | 3575 | FALSE | NO
WPIMACH064 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Dry Run Testing | 8 | 8 | 11-Jun-24 | 19-Jun-24 | WPIMACH063 | LBR | Labor | 4020 | FALSE | NO
WPIMACH084 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Thermoformer Setup | 3 | 3 | 11-Jun-24 | 14-Jun-24 | WPIMACH083 | LBR | Labor | 4732 | FALSE | NO
WPIMACH107 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Extruder Installation | 6 | 6 | 11-May-24 | 17-May-24 | WPIMACH106 | LBR | Labor | 2590 | FALSE | NO
WPIMACH098 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Vendor Selection | 4 | 4 | 11-Nov-23 | 15-Nov-23 | WPIMACH097 | LBR | Labor | 2393 | FALSE | NO
WPIMACH073 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | BOQ Finalization | 5 | 5 | 12-Apr-24 | 17-Apr-24 | WPIMACH072 | LBR | Labor | 5175 | FALSE | NO
WPIMACH095 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Machine Calibration | 4 | 4 | 12-Jan-23 | 16-Jan-23 | WPIMACH094 | LBR | Labor | 739 | FALSE | NO
WPIMACH122 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Vendor Selection | 6 | 6 | 12-Mar-24 | 18-Mar-24 | WPIMACH121 | LBR | Labor | 4050 | FALSE | NO
WPIMACH092 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Thermoformer Setup | 5 | 5 | 12-Sep-23 | 17-Sep-23 | WPIMACH091 | LBR | Labor | 3035 | FALSE | NO
WPIMACH057 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | BOQ Finalization | 4 | 4 | 13-Jun-23 | 17-Jun-23 | WPIMACH056 | LBR | Labor | 3664 | FALSE | NO
WPIMACH111 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Machine Calibration | 10 | 10 | 14-Aug-24 | 24-Aug-24 | WPIMACH110 | LBR | Labor | 5606 | FALSE | NO
WPIMACH113 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | BOQ Finalization | 10 | 10 | 14-Jul-23 | 24-Jul-23 | WPIMACH112 | LBR | Labor | 2224 | FALSE | NO
WPIMACH039 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Machine Calibration | 8 | 8 | 14-Jun-24 | 22-Jun-24 | WPIMACH038 | LBR | Labor | 2260 | FALSE | NO
WPIMACH016 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Dry Run Testing | 3 | 3 | 14-Mar-24 | 17-Mar-24 | WPIMACH015 | LBR | Labor | 5000 | FALSE | NO
WPIMACH082 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Vendor Selection | 10 | 10 | 14-Nov-23 | 24-Nov-23 | WPIMACH081 | LBR | Labor | 1555 | FALSE | NO
WPIMACH035 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Extruder Installation | 6 | 6 | 15-Dec-23 | 21-Dec-23 | WPIMACH034 | LBR | Labor | 8392 | FALSE | NO
WPIMACH008 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Dry Run Testing | 7 | 7 | 15-Sep-23 | 22-Sep-23 | WPIMACH007 | LBR | Labor | 8672 | FALSE | NO
WPIMACH001 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | BOQ Finalization | 6 | 6 | 17-Apr-24 | 23-Apr-24 |  | LBR | Labor | 3181 | FALSE | NO
WPIMACH129 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | BOQ Finalization | 5 | 5 | 17-Dec-23 | 22-Dec-23 | WPIMACH128 | LBR | Labor | 9182 | FALSE | NO
WPIMACH075 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Extruder Installation | 10 | 10 | 17-Jan-23 | 27-Jan-23 | WPIMACH074 | LBR | Labor | 786 | FALSE | NO
WPIMACH061 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Printing Machine Setup | 5 | 5 | 17-Jul-23 | 22-Jul-23 | WPIMACH060 | LBR | Labor | 9788 | FALSE | NO
WPIMACH086 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Robotic Arm Integration | 4 | 4 | 17-Jul-23 | 21-Jul-23 | WPIMACH085 | LBR | Labor | 5204 | FALSE | NO
WPIMACH002 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Vendor Selection | 10 | 10 | 17-Jun-24 | 27-Jun-24 | WPIMACH001 | LBR | Labor | 4604 | FALSE | NO
WPIMACH110 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Robotic Arm Integration | 8 | 8 | 17-May-23 | 25-May-23 | WPIMACH109 | LBR | Labor | 8166 | FALSE | NO
WPIMACH117 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Printing Machine Setup | 10 | 10 | 17-May-24 | 27-May-24 | WPIMACH116 | LBR | Labor | 7125 | FALSE | NO
WPIMACH074 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Vendor Selection | 6 | 6 | 18-Apr-23 | 24-Apr-23 | WPIMACH073 | LBR | Labor | 4728 | FALSE | NO
WPIMACH130 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Vendor Selection | 4 | 4 | 18-Apr-23 | 22-Apr-23 | WPIMACH129 | LBR | Labor | 3954 | FALSE | NO
WPIMACH027 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Extruder Installation | 5 | 5 | 18-Jul-24 | 23-Jul-24 | WPIMACH026 | LBR | Labor | 9277 | FALSE | NO
WPIMACH105 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | BOQ Finalization | 5 | 5 | 18-Nov-23 | 23-Nov-23 | WPIMACH104 | LBR | Labor | 9083 | FALSE | NO
WPIMACH005 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Printing Machine Setup | 5 | 5 | 19-Jan-23 | 24-Jan-23 | WPIMACH004 | LBR | Labor | 2312 | FALSE | NO
WPIMACH033 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | BOQ Finalization | 9 | 9 | 19-Jan-23 | 28-Jan-23 | WPIMACH032 | LBR | Labor | 4539 | FALSE | NO
WPIMACH099 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Extruder Installation | 5 | 5 | 19-Jul-24 | 24-Jul-24 | WPIMACH098 | LBR | Labor | 3323 | FALSE | NO
WPIMACH063 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Machine Calibration | 6 | 6 | 19-Mar-23 | 25-Mar-23 | WPIMACH062 | LBR | Labor | 7064 | FALSE | NO
WPIMACH128 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Dry Run Testing | 3 | 3 | 20-Dec-23 | 23-Dec-23 | WPIMACH127 | LBR | Labor | 6773 | FALSE | NO
WPIMACH049 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | BOQ Finalization | 7 | 7 | 20-Jan-24 | 27-Jan-24 | WPIMACH048 | LBR | Labor | 1931 | FALSE | NO
WPIMACH104 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Dry Run Testing | 4 | 4 | 21-Aug-23 | 25-Aug-23 | WPIMACH103 | LBR | Labor | 7803 | FALSE | NO
WPIMACH019 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Extruder Installation | 3 | 3 | 21-Feb-24 | 24-Feb-24 | WPIMACH018 | LBR | Labor | 2654 | FALSE | NO
WPIMACH090 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Vendor Selection | 8 | 8 | 21-Feb-24 | 29-Feb-24 | WPIMACH089 | LBR | Labor | 5138 | FALSE | NO
WPIMACH078 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Robotic Arm Integration | 10 | 10 | 21-May-23 | 31-May-23 | WPIMACH077 | LBR | Labor | 7630 | FALSE | NO
WPIMACH079 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Machine Calibration | 7 | 7 | 22-Aug-23 | 29-Aug-23 | WPIMACH078 | LBR | Labor | 814 | FALSE | NO
WPIMACH124 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Thermoformer Setup | 6 | 6 | 22-Aug-23 | 28-Aug-23 | WPIMACH123 | LBR | Labor | 5552 | FALSE | NO
WPIMACH030 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Robotic Arm Integration | 5 | 5 | 22-Dec-23 | 27-Dec-23 | WPIMACH029 | LBR | Labor | 1213 | FALSE | NO
WPIMACH032 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Dry Run Testing | 6 | 6 | 22-Jul-24 | 28-Jul-24 | WPIMACH031 | LBR | Labor | 3623 | FALSE | NO
WPIMACH125 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Printing Machine Setup | 3 | 3 | 22-Jun-23 | 25-Jun-23 | WPIMACH124 | LBR | Labor | 9105 | FALSE | NO
WPIMACH021 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Printing Machine Setup | 3 | 3 | 22-Nov-23 | 25-Nov-23 | WPIMACH020 | LBR | Labor | 7946 | FALSE | NO
WPIMACH009 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | BOQ Finalization | 4 | 4 | 23-Aug-24 | 27-Aug-24 | WPIMACH008 | LBR | Labor | 1689 | FALSE | NO
WPIMACH070 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Robotic Arm Integration | 6 | 6 | 23-Jan-24 | 29-Jan-24 | WPIMACH069 | LBR | Labor | 9385 | FALSE | NO
WPIMACH060 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Thermoformer Setup | 10 | 10 | 23-Jun-23 | 03-Jul-23 | WPIMACH059 | LBR | Labor | 3065 | FALSE | NO
WPIMACH025 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | BOQ Finalization | 10 | 10 | 23-Nov-23 | 03-Dec-23 | WPIMACH024 | LBR | Labor | 8815 | FALSE | NO
WPIMACH050 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Vendor Selection | 9 | 9 | 23-Sep-23 | 02-Oct-23 | WPIMACH049 | LBR | Labor | 2559 | FALSE | NO
WPIMACH097 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | BOQ Finalization | 6 | 6 | 24-Apr-23 | 30-Apr-23 | WPIMACH096 | LBR | Labor | 8882 | FALSE | NO
WPIMACH052 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Thermoformer Setup | 6 | 6 | 24-Apr-24 | 30-Apr-24 | WPIMACH051 | LBR | Labor | 4425 | FALSE | NO
WPIMACH026 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Vendor Selection | 10 | 10 | 24-Jan-23 | 03-Feb-23 | WPIMACH025 | LBR | Labor | 9307 | FALSE | NO
WPIMACH058 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Vendor Selection | 5 | 5 | 24-Jul-23 | 29-Jul-23 | WPIMACH057 | LBR | Labor | 8725 | FALSE | NO
WPIMACH045 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Printing Machine Setup | 6 | 6 | 25-Aug-23 | 31-Aug-23 | WPIMACH044 | LBR | Labor | 9947 | FALSE | NO
WPIMACH059 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Extruder Installation | 7 | 7 | 25-Jan-24 | 01-Feb-24 | WPIMACH058 | LBR | Labor | 3284 | FALSE | NO
WPIMACH066 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Vendor Selection | 7 | 7 | 25-Mar-24 | 01-Apr-24 | WPIMACH065 | LBR | Labor | 8988 | FALSE | NO
WPIMACH006 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Robotic Arm Integration | 8 | 8 | 26-Aug-23 | 03-Sep-23 | WPIMACH005 | LBR | Labor | 6456 | FALSE | NO
WPIMACH043 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Extruder Installation | 3 | 3 | 26-Feb-24 | 29-Feb-24 | WPIMACH042 | LBR | Labor | 9765 | FALSE | NO
WPIMACH083 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Extruder Installation | 4 | 4 | 26-Feb-24 | 01-Mar-24 | WPIMACH082 | LBR | Labor | 7655 | FALSE | NO
WPIMACH121 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | BOQ Finalization | 8 | 8 | 26-Jan-24 | 03-Feb-24 | WPIMACH120 | LBR | Labor | 8902 | FALSE | NO
WPIMACH068 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Thermoformer Setup | 6 | 6 | 26-Jun-23 | 02-Jul-23 | WPIMACH067 | LBR | Labor | 2938 | FALSE | NO
WPIMACH069 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Printing Machine Setup | 3 | 3 | 26-Jun-24 | 29-Jun-24 | WPIMACH068 | LBR | Labor | 2194 | FALSE | NO
WPIMACH046 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Robotic Arm Integration | 5 | 5 | 27-Apr-23 | 02-May-23 | WPIMACH045 | LBR | Labor | 5440 | FALSE | NO
WPIMACH010 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Vendor Selection | 4 | 4 | 27-Jan-24 | 31-Jan-24 | WPIMACH009 | LBR | Labor | 9275 | FALSE | NO
WPIMACH076 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Thermoformer Setup | 9 | 9 | 27-Jan-24 | 05-Feb-24 | WPIMACH075 | LBR | Labor | 3326 | FALSE | NO
WPIMACH028 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Thermoformer Setup | 6 | 6 | 27-Nov-23 | 03-Dec-23 | WPIMACH027 | LBR | Labor | 7139 | FALSE | NO
WPIMACH055 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Machine Calibration | 6 | 6 | 28-Apr-24 | 04-May-24 | WPIMACH054 | LBR | Labor | 2407 | FALSE | NO
WPIMACH071 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Machine Calibration | 3 | 3 | 28-Feb-23 | 03-Mar-23 | WPIMACH070 | LBR | Labor | 8630 | FALSE | NO
WPIMACH116 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Thermoformer Setup | 10 | 10 | 28-Feb-24 | 09-Mar-24 | WPIMACH115 | LBR | Labor | 7526 | FALSE | NO
WPIMACH100 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Thermoformer Setup | 4 | 4 | 28-Jan-23 | 01-Feb-23 | WPIMACH099 | LBR | Labor | 1786 | FALSE | NO
WPIMACH087 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Machine Calibration | 6 | 6 | 28-Jul-23 | 03-Aug-23 | WPIMACH086 | LBR | Labor | 5249 | FALSE | NO
WPIMACH091 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Extruder Installation | 10 | 10 | 28-Nov-23 | 08-Dec-23 | WPIMACH090 | LBR | Labor | 4714 | FALSE | NO
WPIMACH093 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Printing Machine Setup | 9 | 9 | 28-Oct-23 | 06-Nov-23 | WPIMACH092 | LBR | Labor | 3450 | FALSE | NO
WPIMACH115 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Extruder Installation | 5 | 5 | 28-Oct-23 | 02-Nov-23 | WPIMACH114 | LBR | Labor | 9136 | FALSE | NO
WPIMACH081 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | BOQ Finalization | 6 | 6 | 29-Apr-23 | 05-May-23 | WPIMACH080 | LBR | Labor | 1200 | FALSE | NO
WPIMACH085 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Printing Machine Setup | 4 | 4 | 29-Apr-23 | 03-May-23 | WPIMACH084 | LBR | Labor | 8927 | FALSE | NO
WPIMACH011 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Extruder Installation | 3 | 3 | 29-Apr-24 | 02-May-24 | WPIMACH010 | LBR | Labor | 1815 | FALSE | NO
WPIMACH018 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Vendor Selection | 10 | 10 | 30-Dec-23 | 09-Jan-24 | WPIMACH017 | LBR | Labor | 552 | FALSE | NO
WPIMACH012 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Thermoformer Setup | 7 | 7 | 30-Jan-24 | 06-Feb-24 | WPIMACH011 | LBR | Labor | 2232 | FALSE | NO
WPIMACH023 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Machine Calibration | 10 | 10 | 30-Mar-24 | 09-Apr-24 | WPIMACH022 | LBR | Labor | 1582 | FALSE | NO
WPIMACH054 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Robotic Arm Integration | 5 | 5 | 31-Jan-24 | 05-Feb-24 | WPIMACH053 | LBR | Labor | 6311 | FALSE | NO
WPIMACH088 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Dry Run Testing | 9 | 9 | 31-May-23 | 09-Jun-23 | WPIMACH087 | LBR | Labor | 1957 | FALSE | NO
WPIMECH093 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Place Compressors | 7 | 7 | 01-Feb-24 | 08-Feb-24 | WPIMECH092 | LBR | Labor | 1941 | FALSE | NO
WPIMECH036 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install HVAC Ducting | 4 | 4 | 01-Jul-23 | 05-Jul-23 | WPIMECH035 | LBR | Labor | 8900 | FALSE | NO
WPIMECH077 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Mechanical Testing & Commissioning | 5 | 5 | 01-May-24 | 06-May-24 | WPIMECH076 | LBR | Labor | 6080 | FALSE | NO
WPIMECH023 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Place Compressors | 9 | 9 | 02-Apr-23 | 11-Apr-23 | WPIMECH022 | LBR | Labor | 3554 | FALSE | NO
WPIMECH034 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | QA/QC of Mechanical Works | 8 | 8 | 02-Aug-24 | 10-Aug-24 | WPIMECH033 | LBR | Labor | 1358 | FALSE | NO
WPIMECH092 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install HVAC Ducting | 3 | 3 | 02-Feb-23 | 05-Feb-23 | WPIMECH091 | LBR | Labor | 2661 | FALSE | NO
WPIMECH089 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install Fire Safety Systems | 9 | 9 | 02-Feb-24 | 11-Feb-24 | WPIMECH088 | LBR | Labor | 3170 | FALSE | NO
WPIMECH042 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Mechanical Testing & Commissioning | 8 | 8 | 02-Jun-23 | 10-Jun-23 | WPIMECH041 | LBR | Labor | 7520 | FALSE | NO
WPIMECH087 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install Heat Controllers | 9 | 9 | 02-Jun-24 | 11-Jun-24 | WPIMECH086 | LBR | Labor | 1110 | FALSE | NO
WPIMECH103 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install Fire Safety Systems | 6 | 6 | 02-Mar-24 | 08-Mar-24 | WPIMECH102 | LBR | Labor | 4119 | FALSE | NO
WPIMECH078 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install HVAC Ducting | 9 | 9 | 02-May-24 | 11-May-24 | WPIMECH077 | LBR | Labor | 4209 | FALSE | NO
WPIMECH091 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Mechanical Testing & Commissioning | 4 | 4 | 03-Apr-23 | 07-Apr-23 | WPIMECH090 | LBR | Labor | 3375 | FALSE | NO
WPIMECH047 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install Fire Safety Systems | 5 | 5 | 03-Feb-23 | 08-Feb-23 | WPIMECH046 | LBR | Labor | 9631 | FALSE | NO
WPIMECH048 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | QA/QC of Mechanical Works | 10 | 10 | 03-Mar-24 | 13-Mar-24 | WPIMECH047 | LBR | Labor | 5607 | FALSE | NO
WPIMECH006 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | QA/QC of Mechanical Works | 4 | 4 | 03-May-24 | 07-May-24 | WPIMECH005 | LBR | Labor | 5592 | FALSE | NO
WPIMECH043 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install HVAC Ducting | 3 | 3 | 04-Apr-23 | 07-Apr-23 | WPIMECH042 | LBR | Labor | 2780 | FALSE | NO
WPIMECH013 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | QA/QC of Mechanical Works | 4 | 4 | 04-Feb-23 | 08-Feb-23 | WPIMECH012 | LBR | Labor | 6368 | FALSE | NO
WPIMECH069 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | QA/QC of Mechanical Works | 10 | 10 | 04-Jul-23 | 14-Jul-23 | WPIMECH068 | LBR | Labor | 8638 | FALSE | NO
WPIMECH081 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Chiller Placement | 3 | 3 | 05-Aug-23 | 08-Aug-23 | WPIMECH080 | LBR | Labor | 8168 | FALSE | NO
WPIMECH031 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install Heat Controllers | 8 | 8 | 05-Feb-24 | 13-Feb-24 | WPIMECH030 | LBR | Labor | 9962 | FALSE | NO
WPIMECH058 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Place Compressors | 9 | 9 | 05-Jan-23 | 14-Jan-23 | WPIMECH057 | LBR | Labor | 3701 | FALSE | NO
WPIMECH016 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Place Compressors | 7 | 7 | 05-Jul-23 | 12-Jul-23 | WPIMECH015 | LBR | Labor | 5508 | FALSE | NO
WPIMECH101 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install Heat Controllers | 5 | 5 | 05-May-24 | 10-May-24 | WPIMECH100 | LBR | Labor | 9871 | FALSE | NO
WPIMECH120 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install HVAC Ducting | 3 | 3 | 05-May-24 | 08-May-24 | WPIMECH119 | LBR | Labor | 1059 | FALSE | NO
WPIMECH098 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Mechanical Testing & Commissioning | 8 | 8 | 06-Apr-23 | 14-Apr-23 | WPIMECH097 | LBR | Labor | 9285 | FALSE | NO
WPIMECH020 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | QA/QC of Mechanical Works | 3 | 3 | 06-Apr-24 | 09-Apr-24 | WPIMECH019 | LBR | Labor | 2563 | FALSE | NO
WPIMECH102 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Chiller Placement | 3 | 3 | 06-Apr-24 | 09-Apr-24 | WPIMECH101 | LBR | Labor | 5067 | FALSE | NO
WPIMECH059 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install Heat Controllers | 4 | 4 | 06-Jan-23 | 10-Jan-23 | WPIMECH058 | LBR | Labor | 1746 | FALSE | NO
WPIMECH053 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Chiller Placement | 8 | 8 | 06-Jan-24 | 14-Jan-24 | WPIMECH052 | LBR | Labor | 854 | FALSE | NO
WPIMECH097 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | QA/QC of Mechanical Works | 7 | 7 | 06-Jun-23 | 13-Jun-23 | WPIMECH096 | LBR | Labor | 704 | FALSE | NO
WPIMECH017 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install Heat Controllers | 6 | 6 | 06-May-23 | 12-May-23 | WPIMECH016 | LBR | Labor | 3407 | FALSE | NO
WPIMECH114 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Place Compressors | 9 | 9 | 06-Oct-23 | 15-Oct-23 | WPIMECH113 | LBR | Labor | 4030 | FALSE | NO
WPIMECH064 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install HVAC Ducting | 3 | 3 | 07-Aug-23 | 10-Aug-23 | WPIMECH063 | LBR | Labor | 1269 | FALSE | NO
WPIMECH075 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install Fire Safety Systems | 7 | 7 | 07-Feb-24 | 14-Feb-24 | WPIMECH074 | LBR | Labor | 683 | FALSE | NO
WPIMECH028 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Mechanical Testing & Commissioning | 7 | 7 | 07-Jan-24 | 14-Jan-24 | WPIMECH027 | LBR | Labor | 9549 | FALSE | NO
WPIMECH039 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Chiller Placement | 9 | 9 | 08-Apr-23 | 17-Apr-23 | WPIMECH038 | LBR | Labor | 4042 | FALSE | NO
WPIMECH008 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install HVAC Ducting | 10 | 10 | 08-Jan-23 | 18-Jan-23 | WPIMECH007 | LBR | Labor | 8847 | FALSE | NO
WPIMECH021 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Mechanical Testing & Commissioning | 4 | 4 | 08-Jan-24 | 12-Jan-24 | WPIMECH020 | LBR | Labor | 4753 | FALSE | NO
WPIMECH088 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Chiller Placement | 9 | 9 | 08-Jul-23 | 17-Jul-23 | WPIMECH087 | LBR | Labor | 6596 | FALSE | NO
WPIMECH033 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install Fire Safety Systems | 6 | 6 | 08-Jun-23 | 14-Jun-23 | WPIMECH032 | LBR | Labor | 7195 | FALSE | NO
WPIMECH060 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Chiller Placement | 8 | 8 | 08-Oct-23 | 16-Oct-23 | WPIMECH059 | LBR | Labor | 4619 | FALSE | NO
WPIMECH062 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | QA/QC of Mechanical Works | 9 | 9 | 09-Aug-24 | 18-Aug-24 | WPIMECH061 | LBR | Labor | 2861 | FALSE | NO
WPIMECH085 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install HVAC Ducting | 5 | 5 | 09-Dec-23 | 14-Dec-23 | WPIMECH084 | LBR | Labor | 693 | FALSE | NO
WPIMECH084 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Mechanical Testing & Commissioning | 8 | 8 | 09-Feb-23 | 17-Feb-23 | WPIMECH083 | LBR | Labor | 9013 | FALSE | NO
WPIMECH112 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Mechanical Testing & Commissioning | 7 | 7 | 09-Jul-23 | 16-Jul-23 | WPIMECH111 | LBR | Labor | 9125 | FALSE | NO
WPIMECH118 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | QA/QC of Mechanical Works | 6 | 6 | 09-Jul-24 | 15-Jul-24 | WPIMECH117 | LBR | Labor | 2749 | FALSE | NO
WPIMECH063 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Mechanical Testing & Commissioning | 7 | 7 | 09-May-24 | 16-May-24 | WPIMECH062 | LBR | Labor | 2759 | FALSE | NO
WPIMECH030 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Place Compressors | 7 | 7 | 09-Oct-23 | 16-Oct-23 | WPIMECH029 | LBR | Labor | 5118 | FALSE | NO
WPIMECH074 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Chiller Placement | 7 | 7 | 10-Feb-23 | 17-Feb-23 | WPIMECH073 | LBR | Labor | 9848 | FALSE | NO
WPIMECH113 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install HVAC Ducting | 7 | 7 | 10-Nov-23 | 17-Nov-23 | WPIMECH112 | LBR | Labor | 8263 | FALSE | NO
WPIMECH119 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Mechanical Testing & Commissioning | 3 | 3 | 11-May-23 | 14-May-23 | WPIMECH118 | LBR | Labor | 1114 | FALSE | NO
WPIMECH038 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install Heat Controllers | 3 | 3 | 12-Dec-23 | 15-Dec-23 | WPIMECH037 | LBR | Labor | 686 | FALSE | NO
WPIMECH115 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install Heat Controllers | 6 | 6 | 12-Dec-23 | 18-Dec-23 | WPIMECH114 | LBR | Labor | 5972 | FALSE | NO
WPIMECH096 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install Fire Safety Systems | 8 | 8 | 12-May-23 | 20-May-23 | WPIMECH095 | LBR | Labor | 9820 | FALSE | NO
WPIMECH099 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install HVAC Ducting | 5 | 5 | 12-Oct-23 | 17-Oct-23 | WPIMECH098 | LBR | Labor | 4779 | FALSE | NO
WPIMECH029 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install HVAC Ducting | 3 | 3 | 13-Dec-23 | 16-Dec-23 | WPIMECH028 | LBR | Labor | 8663 | FALSE | NO
WPIMECH010 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install Heat Controllers | 9 | 9 | 13-Feb-23 | 22-Feb-23 | WPIMECH009 | LBR | Labor | 6747 | FALSE | NO
WPIMECH032 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Chiller Placement | 8 | 8 | 13-Jul-23 | 21-Jul-23 | WPIMECH031 | LBR | Labor | 7810 | FALSE | NO
WPIMECH100 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Place Compressors | 8 | 8 | 13-Jun-24 | 21-Jun-24 | WPIMECH099 | LBR | Labor | 5458 | FALSE | NO
WPIMECH094 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install Heat Controllers | 10 | 10 | 13-Mar-23 | 23-Mar-23 | WPIMECH093 | LBR | Labor | 1408 | FALSE | NO
WPIMECH109 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Chiller Placement | 3 | 3 | 13-Sep-23 | 16-Sep-23 | WPIMECH108 | LBR | Labor | 2850 | FALSE | NO
WPIMECH117 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install Fire Safety Systems | 3 | 3 | 14-Jun-23 | 17-Jun-23 | WPIMECH116 | LBR | Labor | 2311 | FALSE | NO
WPIMECH066 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install Heat Controllers | 8 | 8 | 15-Dec-23 | 23-Dec-23 | WPIMECH065 | LBR | Labor | 6073 | FALSE | NO
WPIMECH044 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Place Compressors | 4 | 4 | 15-Jun-24 | 19-Jun-24 | WPIMECH043 | LBR | Labor | 627 | FALSE | NO
WPIMECH110 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install Fire Safety Systems | 3 | 3 | 15-Mar-23 | 18-Mar-23 | WPIMECH109 | LBR | Labor | 1948 | FALSE | NO
WPIMECH019 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install Fire Safety Systems | 7 | 7 | 16-Aug-23 | 23-Aug-23 | WPIMECH018 | LBR | Labor | 2411 | FALSE | NO
WPIMECH083 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | QA/QC of Mechanical Works | 9 | 9 | 16-Jun-24 | 25-Jun-24 | WPIMECH082 | LBR | Labor | 6916 | FALSE | NO
WPIMECH055 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | QA/QC of Mechanical Works | 5 | 5 | 16-May-23 | 21-May-23 | WPIMECH054 | LBR | Labor | 9792 | FALSE | NO
WPIMECH107 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Place Compressors | 7 | 7 | 17-Aug-24 | 24-Aug-24 | WPIMECH106 | LBR | Labor | 2664 | FALSE | NO
WPIMECH090 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | QA/QC of Mechanical Works | 3 | 3 | 17-Feb-24 | 20-Feb-24 | WPIMECH089 | LBR | Labor | 9753 | FALSE | NO
WPIMECH002 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Place Compressors | 7 | 7 | 17-Jan-23 | 24-Jan-23 | WPIMECH001 | LBR | Labor | 8187 | FALSE | NO
WPIMECH095 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Chiller Placement | 9 | 9 | 17-Jul-23 | 26-Jul-23 | WPIMECH094 | LBR | Labor | 731 | FALSE | NO
WPIMECH022 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install HVAC Ducting | 4 | 4 | 17-Jun-23 | 21-Jun-23 | WPIMECH021 | LBR | Labor | 5077 | FALSE | NO
WPIMECH082 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install Fire Safety Systems | 8 | 8 | 17-May-23 | 25-May-23 | WPIMECH081 | LBR | Labor | 5416 | FALSE | NO
WPIMECH037 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Place Compressors | 3 | 3 | 17-Sep-23 | 20-Sep-23 | WPIMECH036 | LBR | Labor | 851 | FALSE | NO
WPIMECH040 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install Fire Safety Systems | 6 | 6 | 18-Apr-23 | 24-Apr-23 | WPIMECH039 | LBR | Labor | 4873 | FALSE | NO
WPIMECH015 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install HVAC Ducting | 8 | 8 | 18-Aug-24 | 26-Aug-24 | WPIMECH014 | LBR | Labor | 9119 | FALSE | NO
WPIMECH056 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Mechanical Testing & Commissioning | 9 | 9 | 18-Dec-23 | 27-Dec-23 | WPIMECH055 | LBR | Labor | 2424 | FALSE | NO
WPIMECH045 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install Heat Controllers | 9 | 9 | 18-Jan-23 | 27-Jan-23 | WPIMECH044 | LBR | Labor | 2604 | FALSE | NO
WPIMECH061 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install Fire Safety Systems | 3 | 3 | 18-May-24 | 21-May-24 | WPIMECH060 | LBR | Labor | 1244 | FALSE | NO
WPIMECH073 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install Heat Controllers | 5 | 5 | 19-Jul-24 | 24-Jul-24 | WPIMECH072 | LBR | Labor | 6070 | FALSE | NO
WPIMECH012 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install Fire Safety Systems | 8 | 8 | 19-Nov-23 | 27-Nov-23 | WPIMECH011 | LBR | Labor | 9019 | FALSE | NO
WPIMECH106 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install HVAC Ducting | 5 | 5 | 20-May-23 | 25-May-23 | WPIMECH105 | LBR | Labor | 3572 | FALSE | NO
WPIMECH001 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install HVAC Ducting | 4 | 4 | 20-May-24 | 24-May-24 |  | LBR | Labor | 3763 | FALSE | NO
WPIMECH005 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install Fire Safety Systems | 5 | 5 | 21-Aug-24 | 26-Aug-24 | WPIMECH004 | LBR | Labor | 4907 | FALSE | NO
WPIMECH104 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | QA/QC of Mechanical Works | 4 | 4 | 21-Aug-24 | 25-Aug-24 | WPIMECH103 | LBR | Labor | 6009 | FALSE | NO
WPIMECH046 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Chiller Placement | 3 | 3 | 21-Feb-24 | 24-Feb-24 | WPIMECH045 | LBR | Labor | 8914 | FALSE | NO
WPIMECH054 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install Fire Safety Systems | 5 | 5 | 21-Jun-23 | 26-Jun-23 | WPIMECH053 | LBR | Labor | 7881 | FALSE | NO
WPIMECH071 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install HVAC Ducting | 6 | 6 | 21-Mar-24 | 27-Mar-24 | WPIMECH070 | LBR | Labor | 8720 | FALSE | NO
WPIMECH018 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Chiller Placement | 3 | 3 | 21-May-23 | 24-May-23 | WPIMECH017 | LBR | Labor | 1358 | FALSE | NO
WPIMECH065 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Place Compressors | 5 | 5 | 22-Jan-23 | 27-Jan-23 | WPIMECH064 | LBR | Labor | 6936 | FALSE | NO
WPIMECH009 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Place Compressors | 7 | 7 | 22-Mar-23 | 29-Mar-23 | WPIMECH008 | LBR | Labor | 976 | FALSE | NO
WPIMECH014 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Mechanical Testing & Commissioning | 4 | 4 | 22-May-24 | 26-May-24 | WPIMECH013 | LBR | Labor | 8188 | FALSE | NO
WPIMECH011 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Chiller Placement | 9 | 9 | 22-Nov-23 | 01-Dec-23 | WPIMECH010 | LBR | Labor | 8873 | FALSE | NO
WPIMECH007 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Mechanical Testing & Commissioning | 10 | 10 | 23-Jun-23 | 03-Jul-23 | WPIMECH006 | LBR | Labor | 9106 | FALSE | NO
WPIMECH068 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install Fire Safety Systems | 4 | 4 | 24-Aug-23 | 28-Aug-23 | WPIMECH067 | LBR | Labor | 9772 | FALSE | NO
WPIMECH116 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Chiller Placement | 6 | 6 | 24-Feb-23 | 02-Mar-23 | WPIMECH115 | LBR | Labor | 4681 | FALSE | NO
WPIMECH076 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | QA/QC of Mechanical Works | 5 | 5 | 24-Jan-24 | 29-Jan-24 | WPIMECH075 | LBR | Labor | 3645 | FALSE | NO
WPIMECH050 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install HVAC Ducting | 4 | 4 | 24-Jul-23 | 28-Jul-23 | WPIMECH049 | LBR | Labor | 6714 | FALSE | NO
WPIMECH035 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Mechanical Testing & Commissioning | 5 | 5 | 24-Jul-24 | 29-Jul-24 | WPIMECH034 | LBR | Labor | 2577 | FALSE | NO
WPIMECH057 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install HVAC Ducting | 5 | 5 | 25-Apr-23 | 30-Apr-23 | WPIMECH056 | LBR | Labor | 6242 | FALSE | NO
WPIMECH003 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install Heat Controllers | 4 | 4 | 25-Dec-23 | 29-Dec-23 | WPIMECH002 | LBR | Labor | 5399 | FALSE | NO
WPIMECH004 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Chiller Placement | 7 | 7 | 25-Mar-24 | 01-Apr-24 | WPIMECH003 | LBR | Labor | 3922 | FALSE | NO
WPIMECH070 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Mechanical Testing & Commissioning | 6 | 6 | 25-Nov-23 | 01-Dec-23 | WPIMECH069 | LBR | Labor | 4253 | FALSE | NO
WPIMECH079 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Place Compressors | 3 | 3 | 26-Dec-23 | 29-Dec-23 | WPIMECH078 | LBR | Labor | 3709 | FALSE | NO
WPIMECH111 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | QA/QC of Mechanical Works | 9 | 9 | 26-Dec-23 | 04-Jan-24 | WPIMECH110 | LBR | Labor | 580 | FALSE | NO
WPIMECH025 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Chiller Placement | 6 | 6 | 26-Feb-24 | 03-Mar-24 | WPIMECH024 | LBR | Labor | 2391 | FALSE | NO
WPIMECH026 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install Fire Safety Systems | 5 | 5 | 26-May-24 | 31-May-24 | WPIMECH025 | LBR | Labor | 5591 | FALSE | NO
WPIMECH108 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install Heat Controllers | 7 | 7 | 26-May-24 | 02-Jun-24 | WPIMECH107 | LBR | Labor | 3696 | FALSE | NO
WPIMECH067 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Chiller Placement | 8 | 8 | 26-Nov-23 | 04-Dec-23 | WPIMECH066 | LBR | Labor | 9963 | FALSE | NO
WPIMECH049 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Mechanical Testing & Commissioning | 10 | 10 | 27-Apr-24 | 07-May-24 | WPIMECH048 | LBR | Labor | 8496 | FALSE | NO
WPIMECH086 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Place Compressors | 10 | 10 | 28-Apr-24 | 08-May-24 | WPIMECH085 | LBR | Labor | 5318 | FALSE | NO
WPIMECH027 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | QA/QC of Mechanical Works | 6 | 6 | 28-Nov-23 | 04-Dec-23 | WPIMECH026 | LBR | Labor | 2226 | FALSE | NO
WPIMECH041 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | QA/QC of Mechanical Works | 3 | 3 | 28-Oct-23 | 31-Oct-23 | WPIMECH040 | LBR | Labor | 3022 | FALSE | NO
WPIMECH080 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install Heat Controllers | 9 | 9 | 29-Aug-23 | 07-Sep-23 | WPIMECH079 | LBR | Labor | 3102 | FALSE | NO
WPIMECH051 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Place Compressors | 4 | 4 | 29-Jun-23 | 03-Jul-23 | WPIMECH050 | LBR | Labor | 5187 | FALSE | NO
WPIMECH024 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install Heat Controllers | 6 | 6 | 29-Sep-23 | 05-Oct-23 | WPIMECH023 | LBR | Labor | 7026 | FALSE | NO
WPIMECH052 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Install Heat Controllers | 3 | 3 | 30-May-23 | 02-Jun-23 | WPIMECH051 | LBR | Labor | 5592 | FALSE | NO
WPIMECH105 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Mechanical Testing & Commissioning | 8 | 8 | 30-Nov-23 | 08-Dec-23 | WPIMECH104 | LBR | Labor | 5251 | FALSE | NO
WPIMECH072 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Place Compressors | 4 | 4 | 31-May-24 | 04-Jun-24 | WPIMECH071 | LBR | Labor | 8128 | FALSE | NO
WPIPRD053 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Production Process Optimization | 4 | 4 | 01-Jul-23 | 05-Jul-23 | WPIPRD052 | LBR | Labor | 2335 | FALSE | NO
WPIPRD056 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Resin Storage & Quality Checks | 5 | 5 | 01-Jul-23 | 06-Jul-23 | WPIPRD055 | MTR | Material | 2534 | FALSE | NO
WPIPRD079 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Resin Procurement | 3 | 3 | 01-Jun-24 | 04-Jun-24 | WPIPRD078 | MTR | Material | 5743 | FALSE | NO
WPIPRD005 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Production Process Optimization | 3 | 3 | 01-May-23 | 04-May-23 | WPIPRD004 | LBR | Labor | 1313 | FALSE | NO
WPIPRD006 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Final Production Handover | 9 | 9 | 02-Aug-23 | 11-Aug-23 | WPIPRD005 | LBR | Labor | 5624 | FALSE | NO
WPIPRD048 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Final Production Handover | 8 | 8 | 02-Jan-24 | 10-Jan-24 | WPIPRD047 | LBR | Labor | 573 | FALSE | NO
WPIPRD037 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Resin Procurement | 7 | 7 | 03-Apr-24 | 10-Apr-24 | WPIPRD036 | MTR | Material | 2685 | FALSE | NO
WPIPRD076 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Operator Staff Training | 7 | 7 | 03-Apr-24 | 10-Apr-24 | WPIPRD075 | LBR | Labor | 8266 | FALSE | NO
WPIPRD071 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Production Process Optimization | 8 | 8 | 03-Feb-23 | 11-Feb-23 | WPIPRD070 | LBR | Labor | 3151 | FALSE | NO
WPIPRD109 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Resin Procurement | 10 | 10 | 03-Jun-23 | 13-Jun-23 | WPIPRD108 | MTR | Material | 1178 | FALSE | NO
WPIPRD086 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Resin Storage & Quality Checks | 10 | 10 | 03-Mar-23 | 13-Mar-23 | WPIPRD085 | MTR | Material | 9107 | FALSE | NO
WPIPRD045 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Production Trials | 7 | 7 | 03-Mar-24 | 10-Mar-24 | WPIPRD044 | LBR | Labor | 4097 | FALSE | NO
WPIPRD013 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Resin Procurement | 5 | 5 | 03-May-24 | 08-May-24 | WPIPRD012 | MTR | Material | 7768 | FALSE | NO
WPIPRD063 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Production Trials | 9 | 9 | 03-Sep-23 | 12-Sep-23 | WPIPRD062 | LBR | Labor | 9606 | FALSE | NO
WPIPRD062 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Resin Storage & Quality Checks | 6 | 6 | 04-Apr-23 | 10-Apr-23 | WPIPRD061 | MTR | Material | 8176 | FALSE | NO
WPIPRD010 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Operator Staff Training | 4 | 4 | 04-Apr-24 | 08-Apr-24 | WPIPRD009 | LBR | Labor | 557 | FALSE | NO
WPIPRD117 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Production Trials | 3 | 3 | 04-Feb-23 | 07-Feb-23 | WPIPRD116 | LBR | Labor | 8874 | FALSE | NO
WPIPRD017 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Production Process Optimization | 9 | 9 | 04-Jun-23 | 13-Jun-23 | WPIPRD016 | LBR | Labor | 9063 | FALSE | NO
WPIPRD119 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Production Process Optimization | 7 | 7 | 04-Jun-24 | 11-Jun-24 | WPIPRD118 | LBR | Labor | 949 | FALSE | NO
WPIPRD083 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Production Process Optimization | 5 | 5 | 05-Feb-23 | 10-Feb-23 | WPIPRD082 | LBR | Labor | 5357 | FALSE | NO
WPIPRD034 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Operator Staff Training | 10 | 10 | 05-Jul-23 | 15-Jul-23 | WPIPRD033 | LBR | Labor | 7709 | FALSE | NO
WPIPRD008 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Resin Storage & Quality Checks | 10 | 10 | 05-Jun-24 | 15-Jun-24 | WPIPRD007 | MTR | Material | 6680 | FALSE | NO
WPIPRD065 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Production Process Optimization | 9 | 9 | 05-Nov-23 | 14-Nov-23 | WPIPRD064 | LBR | Labor | 1607 | FALSE | NO
WPIPRD047 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Production Process Optimization | 3 | 3 | 05-Oct-23 | 08-Oct-23 | WPIPRD046 | LBR | Labor | 8392 | FALSE | NO
WPIPRD098 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Resin Storage & Quality Checks | 4 | 4 | 06-Apr-23 | 10-Apr-23 | WPIPRD097 | MTR | Material | 6296 | FALSE | NO
WPIPRD096 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Final Production Handover | 3 | 3 | 06-Dec-23 | 09-Dec-23 | WPIPRD095 | LBR | Labor | 8761 | FALSE | NO
WPIPRD035 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Production Process Optimization | 9 | 9 | 06-Jul-23 | 15-Jul-23 | WPIPRD034 | LBR | Labor | 3910 | FALSE | NO
WPIPRD112 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Operator Staff Training | 7 | 7 | 06-Jul-23 | 13-Jul-23 | WPIPRD111 | LBR | Labor | 6927 | FALSE | NO
WPIPRD016 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Operator Staff Training | 5 | 5 | 06-Mar-24 | 11-Mar-24 | WPIPRD015 | LBR | Labor | 4297 | FALSE | NO
WPIPRD110 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Resin Storage & Quality Checks | 5 | 5 | 06-Sep-23 | 11-Sep-23 | WPIPRD109 | MTR | Material | 1243 | FALSE | NO
WPIPRD093 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Production Trials | 9 | 9 | 07-Mar-23 | 16-Mar-23 | WPIPRD092 | LBR | Labor | 7229 | FALSE | NO
WPIPRD104 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Resin Storage & Quality Checks | 5 | 5 | 07-May-24 | 12-May-24 | WPIPRD103 | MTR | Material | 4661 | FALSE | NO
WPIPRD064 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Operator Staff Training | 8 | 8 | 08-Apr-23 | 16-Apr-23 | WPIPRD063 | LBR | Labor | 7698 | FALSE | NO
WPIPRD066 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Final Production Handover | 9 | 9 | 08-Jun-23 | 17-Jun-23 | WPIPRD065 | LBR | Labor | 5317 | FALSE | NO
WPIPRD113 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Production Process Optimization | 3 | 3 | 08-Nov-23 | 11-Nov-23 | WPIPRD112 | LBR | Labor | 9390 | FALSE | NO
WPIPRD097 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Resin Procurement | 8 | 8 | 09-Dec-23 | 17-Dec-23 | WPIPRD096 | MTR | Material | 4326 | FALSE | NO
WPIPRD077 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Production Process Optimization | 7 | 7 | 09-Jun-24 | 16-Jun-24 | WPIPRD076 | LBR | Labor | 2046 | FALSE | NO
WPIPRD114 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Final Production Handover | 9 | 9 | 09-Jun-24 | 18-Jun-24 | WPIPRD113 | LBR | Labor | 634 | FALSE | NO
WPIPRD107 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Production Process Optimization | 6 | 6 | 09-Sep-23 | 15-Sep-23 | WPIPRD106 | LBR | Labor | 7874 | FALSE | NO
WPIPRD108 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Final Production Handover | 9 | 9 | 10-Apr-23 | 19-Apr-23 | WPIPRD107 | LBR | Labor | 1937 | FALSE | NO
WPIPRD111 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Production Trials | 10 | 10 | 10-Dec-23 | 20-Dec-23 | WPIPRD110 | LBR | Labor | 8160 | FALSE | NO
WPIPRD118 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Operator Staff Training | 9 | 9 | 10-Dec-23 | 19-Dec-23 | WPIPRD117 | LBR | Labor | 7447 | FALSE | NO
WPIPRD072 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Final Production Handover | 9 | 9 | 10-Feb-24 | 19-Feb-24 | WPIPRD071 | LBR | Labor | 6503 | FALSE | NO
WPIPRD081 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Production Trials | 4 | 4 | 10-Jun-23 | 14-Jun-23 | WPIPRD080 | LBR | Labor | 3916 | FALSE | NO
WPIPRD059 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Production Process Optimization | 7 | 7 | 10-Jun-24 | 17-Jun-24 | WPIPRD058 | LBR | Labor | 7563 | FALSE | NO
WPIPRD106 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Operator Staff Training | 4 | 4 | 10-Mar-23 | 14-Mar-23 | WPIPRD105 | LBR | Labor | 3300 | FALSE | NO
WPIPRD074 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Resin Storage & Quality Checks | 10 | 10 | 10-Mar-24 | 20-Mar-24 | WPIPRD073 | MTR | Material | 7077 | FALSE | NO
WPIPRD043 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Resin Procurement | 3 | 3 | 10-Nov-23 | 13-Nov-23 | WPIPRD042 | MTR | Material | 607 | FALSE | NO
WPIPRD007 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Resin Procurement | 6 | 6 | 11-Aug-24 | 17-Aug-24 | WPIPRD006 | MTR | Material | 739 | FALSE | NO
WPIPRD004 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Operator Staff Training | 10 | 10 | 11-Mar-23 | 21-Mar-23 | WPIPRD003 | LBR | Labor | 8148 | FALSE | NO
WPIPRD002 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Resin Storage & Quality Checks | 5 | 5 | 11-May-24 | 16-May-24 | WPIPRD001 | MTR | Material | 6913 | FALSE | NO
WPIPRD087 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Production Trials | 9 | 9 | 11-Sep-23 | 20-Sep-23 | WPIPRD086 | LBR | Labor | 5413 | FALSE | NO
WPIPRD012 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Final Production Handover | 8 | 8 | 12-Jun-23 | 20-Jun-23 | WPIPRD011 | LBR | Labor | 9623 | FALSE | NO
WPIPRD036 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Final Production Handover | 5 | 5 | 13-Jan-24 | 18-Jan-24 | WPIPRD035 | LBR | Labor | 852 | FALSE | NO
WPIPRD058 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Operator Staff Training | 10 | 10 | 13-Jul-24 | 23-Jul-24 | WPIPRD057 | LBR | Labor | 2625 | FALSE | NO
WPIPRD091 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Resin Procurement | 9 | 9 | 13-Jun-24 | 22-Jun-24 | WPIPRD090 | MTR | Material | 8103 | FALSE | NO
WPIPRD020 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Resin Storage & Quality Checks | 8 | 8 | 13-May-23 | 21-May-23 | WPIPRD019 | MTR | Material | 8052 | FALSE | NO
WPIPRD024 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Final Production Handover | 4 | 4 | 13-Oct-23 | 17-Oct-23 | WPIPRD023 | LBR | Labor | 2518 | FALSE | NO
WPIPRD031 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Resin Procurement | 4 | 4 | 14-Aug-24 | 18-Aug-24 | WPIPRD030 | MTR | Material | 5561 | FALSE | NO
WPIPRD046 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Operator Staff Training | 9 | 9 | 14-Feb-24 | 23-Feb-24 | WPIPRD045 | LBR | Labor | 3090 | FALSE | NO
WPIPRD026 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Resin Storage & Quality Checks | 6 | 6 | 14-Jan-24 | 20-Jan-24 | WPIPRD025 | MTR | Material | 7196 | FALSE | NO
WPIPRD100 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Operator Staff Training | 8 | 8 | 14-Jul-23 | 22-Jul-23 | WPIPRD099 | LBR | Labor | 2181 | FALSE | NO
WPIPRD102 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Final Production Handover | 8 | 8 | 14-May-23 | 22-May-23 | WPIPRD101 | LBR | Labor | 4349 | FALSE | NO
WPIPRD103 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Resin Procurement | 7 | 7 | 14-Sep-23 | 21-Sep-23 | WPIPRD102 | MTR | Material | 9645 | FALSE | NO
WPIPRD039 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Production Trials | 4 | 4 | 15-Jul-24 | 19-Jul-24 | WPIPRD038 | LBR | Labor | 6669 | FALSE | NO
WPIPRD057 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Production Trials | 5 | 5 | 15-May-24 | 20-May-24 | WPIPRD056 | LBR | Labor | 6606 | FALSE | NO
WPIPRD041 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Production Process Optimization | 4 | 4 | 16-Jan-24 | 20-Jan-24 | WPIPRD040 | LBR | Labor | 7154 | FALSE | NO
WPIPRD019 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Resin Procurement | 8 | 8 | 16-Jun-23 | 24-Jun-23 | WPIPRD018 | MTR | Material | 8635 | FALSE | NO
WPIPRD042 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Final Production Handover | 7 | 7 | 17-Apr-24 | 24-Apr-24 | WPIPRD041 | LBR | Labor | 9604 | FALSE | NO
WPIPRD015 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Production Trials | 7 | 7 | 17-Aug-23 | 24-Aug-23 | WPIPRD014 | LBR | Labor | 1058 | FALSE | NO
WPIPRD022 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Operator Staff Training | 7 | 7 | 17-Aug-23 | 24-Aug-23 | WPIPRD021 | LBR | Labor | 9613 | FALSE | NO
WPIPRD038 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Resin Storage & Quality Checks | 9 | 9 | 17-Aug-24 | 26-Aug-24 | WPIPRD037 | MTR | Material | 9936 | FALSE | NO
WPIPRD101 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Production Process Optimization | 7 | 7 | 17-Dec-23 | 24-Dec-23 | WPIPRD100 | LBR | Labor | 1169 | FALSE | NO
WPIPRD073 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Resin Procurement | 9 | 9 | 17-May-23 | 26-May-23 | WPIPRD072 | MTR | Material | 4218 | FALSE | NO
WPIPRD021 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Production Trials | 9 | 9 | 17-May-24 | 26-May-24 | WPIPRD020 | LBR | Labor | 3512 | FALSE | NO
WPIPRD060 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Final Production Handover | 5 | 5 | 17-Sep-23 | 22-Sep-23 | WPIPRD059 | LBR | Labor | 3886 | FALSE | NO
WPIPRD044 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Resin Storage & Quality Checks | 8 | 8 | 19-Apr-24 | 27-Apr-24 | WPIPRD043 | MTR | Material | 8690 | FALSE | NO
WPIPRD051 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Production Trials | 4 | 4 | 19-Apr-24 | 23-Apr-24 | WPIPRD050 | LBR | Labor | 7065 | FALSE | NO
WPIPRD014 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Resin Storage & Quality Checks | 4 | 4 | 19-Aug-24 | 23-Aug-24 | WPIPRD013 | MTR | Material | 3326 | FALSE | NO
WPIPRD050 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Resin Storage & Quality Checks | 4 | 4 | 19-Jan-24 | 23-Jan-24 | WPIPRD049 | MTR | Material | 4740 | FALSE | NO
WPIPRD054 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Final Production Handover | 9 | 9 | 20-Jan-23 | 29-Jan-23 | WPIPRD053 | LBR | Labor | 8477 | FALSE | NO
WPIPRD052 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Operator Staff Training | 10 | 10 | 20-Jan-24 | 30-Jan-24 | WPIPRD051 | LBR | Labor | 9265 | FALSE | NO
WPIPRD029 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Production Process Optimization | 4 | 4 | 21-Apr-23 | 25-Apr-23 | WPIPRD028 | LBR | Labor | 7354 | FALSE | NO
WPIPRD068 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Resin Storage & Quality Checks | 8 | 8 | 21-Jan-23 | 29-Jan-23 | WPIPRD067 | MTR | Material | 4730 | FALSE | NO
WPIPRD120 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Final Production Handover | 6 | 6 | 21-May-24 | 27-May-24 | WPIPRD119 | LBR | Labor | 3392 | FALSE | NO
WPIPRD099 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Production Trials | 9 | 9 | 21-Sep-23 | 30-Sep-23 | WPIPRD098 | LBR | Labor | 9496 | FALSE | NO
WPIPRD092 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Resin Storage & Quality Checks | 7 | 7 | 22-Feb-23 | 01-Mar-23 | WPIPRD091 | MTR | Material | 2182 | FALSE | NO
WPIPRD030 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Final Production Handover | 5 | 5 | 22-Jul-24 | 27-Jul-24 | WPIPRD029 | LBR | Labor | 8647 | FALSE | NO
WPIPRD075 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Production Trials | 4 | 4 | 22-Nov-23 | 26-Nov-23 | WPIPRD074 | LBR | Labor | 9050 | FALSE | NO
WPIPRD078 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Final Production Handover | 10 | 10 | 23-Apr-24 | 03-May-24 | WPIPRD077 | LBR | Labor | 4306 | FALSE | NO
WPIPRD003 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Production Trials | 4 | 4 | 23-Jul-23 | 27-Jul-23 | WPIPRD002 | LBR | Labor | 1824 | FALSE | NO
WPIPRD095 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Production Process Optimization | 7 | 7 | 23-Jul-24 | 30-Jul-24 | WPIPRD094 | LBR | Labor | 6354 | FALSE | NO
WPIPRD040 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Operator Staff Training | 6 | 6 | 23-Mar-23 | 29-Mar-23 | WPIPRD039 | LBR | Labor | 9793 | FALSE | NO
WPIPRD116 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Resin Storage & Quality Checks | 8 | 8 | 23-May-24 | 31-May-24 | WPIPRD115 | MTR | Material | 2431 | FALSE | NO
WPIPRD082 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Operator Staff Training | 4 | 4 | 23-Sep-23 | 27-Sep-23 | WPIPRD081 | LBR | Labor | 1638 | FALSE | NO
WPIPRD049 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Resin Procurement | 10 | 10 | 24-Jun-24 | 04-Jul-24 | WPIPRD048 | MTR | Material | 3571 | FALSE | NO
WPIPRD094 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Operator Staff Training | 3 | 3 | 24-Jun-24 | 27-Jun-24 | WPIPRD093 | LBR | Labor | 3813 | FALSE | NO
WPIPRD084 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Final Production Handover | 5 | 5 | 24-Mar-23 | 29-Mar-23 | WPIPRD083 | LBR | Labor | 532 | FALSE | NO
WPIPRD088 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Operator Staff Training | 7 | 7 | 24-Sep-23 | 01-Oct-23 | WPIPRD087 | LBR | Labor | 1700 | FALSE | NO
WPIPRD018 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Final Production Handover | 6 | 6 | 25-Apr-23 | 01-May-23 | WPIPRD017 | LBR | Labor | 2756 | FALSE | NO
WPIPRD070 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Operator Staff Training | 6 | 6 | 25-Apr-24 | 01-May-24 | WPIPRD069 | LBR | Labor | 1558 | FALSE | NO
WPIPRD067 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Resin Procurement | 10 | 10 | 25-Jul-23 | 04-Aug-23 | WPIPRD066 | MTR | Material | 3531 | FALSE | NO
WPIPRD089 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Production Process Optimization | 7 | 7 | 25-Jun-23 | 02-Jul-23 | WPIPRD088 | LBR | Labor | 3979 | FALSE | NO
WPIPRD055 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Resin Procurement | 9 | 9 | 25-May-24 | 03-Jun-24 | WPIPRD054 | MTR | Material | 3378 | FALSE | NO
WPIPRD025 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Resin Procurement | 5 | 5 | 26-Apr-23 | 01-May-23 | WPIPRD024 | MTR | Material | 5652 | FALSE | NO
WPIPRD027 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Production Trials | 4 | 4 | 27-Feb-24 | 02-Mar-24 | WPIPRD026 | LBR | Labor | 811 | FALSE | NO
WPIPRD032 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Resin Storage & Quality Checks | 7 | 7 | 27-Jul-24 | 03-Aug-24 | WPIPRD031 | MTR | Material | 1148 | FALSE | NO
WPIPRD061 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Resin Procurement | 3 | 3 | 27-Jul-24 | 30-Jul-24 | WPIPRD060 | MTR | Material | 8050 | FALSE | NO
WPIPRD033 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Production Trials | 5 | 5 | 27-Mar-23 | 01-Apr-23 | WPIPRD032 | LBR | Labor | 986 | FALSE | NO
WPIPRD105 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Production Trials | 5 | 5 | 27-May-24 | 01-Jun-24 | WPIPRD104 | LBR | Labor | 1864 | FALSE | NO
WPIPRD028 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Operator Staff Training | 8 | 8 | 28-Jan-23 | 05-Feb-23 | WPIPRD027 | LBR | Labor | 4021 | FALSE | NO
WPIPRD009 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Production Trials | 6 | 6 | 28-May-24 | 03-Jun-24 | WPIPRD008 | LBR | Labor | 7430 | FALSE | NO
WPIPRD011 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Production Process Optimization | 5 | 5 | 28-Oct-23 | 02-Nov-23 | WPIPRD010 | LBR | Labor | 8460 | FALSE | NO
WPIPRD090 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Final Production Handover | 7 | 7 | 29-Dec-23 | 05-Jan-24 | WPIPRD089 | LBR | Labor | 4432 | FALSE | NO
WPIPRD023 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Production Process Optimization | 4 | 4 | 29-Jun-24 | 03-Jul-24 | WPIPRD022 | LBR | Labor | 4711 | FALSE | NO
WPIPRD115 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Resin Procurement | 3 | 3 | 29-Sep-23 | 02-Oct-23 | WPIPRD114 | MTR | Material | 5361 | FALSE | NO
WPIPRD069 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Production Trials | 6 | 6 | 30-Jul-24 | 05-Aug-24 | WPIPRD068 | LBR | Labor | 9998 | FALSE | NO
WPIPRD001 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Resin Procurement | 7 | 7 | 31-Jan-24 | 07-Feb-24 |  | MTR | Material | 8402 | FALSE | NO
WPIPRD080 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Resin Storage & Quality Checks | 6 | 6 | 31-Jul-24 | 06-Aug-24 | WPIPRD079 | MTR | Material | 8827 | FALSE | NO
WPIPRD085 | Completed | WPI_PlantExpansion_F | WPI_PlantExpansion_FULL | Resin Procurement | 9 | 9 | 31-Jul-24 | 09-Aug-24 | WPIPRD084 | MTR | Material | 698 | FALSE | NO

## TASKPRED
pred_proj_id | proj_id | PREDTASK__PROJWBS__wbs_full_name | TASK__PROJWBS__wbs_full_name | pred_task_id | task_id | PREDTASK__task_name | TASK__task_name | pred_type | lag_hr_cnt | PREDTASK__status_code | TASK__status_code | PREDTASK__rsrc_id | TASK__rsrc_id | delete_record_flag

## RSRC
rsrc_short_name | rsrc_name | rsrc_title_name
Resource ID | Resource Name | Title
MathisL | Lane Mathis, CIO
AndersonG | Glen Anderson, VP Development
VincentI | Ian Vincent
CharlesM | Mandy Charles, VP IT Ops
ZhuS | Shannon Zhu
LaffertyV | Vanessa Lafferty
BennettC | Carina Bennett
PaxsonD | Dan Paxson
SinghD | Deepak Singh
SharpeD | Dan Sharpe
ITCon | IT Consultant
LiR | Roy Li
RiceB | Barbara Rice, PMO Director
ChopraA | Amit Chopra
AbrahamM | Molly Abraham
WrenJ | Jo Wren
ATM ENG | Automation Systems Engineer
IT | Information Technology Group
Product Dev | Product Development Resources
ManufEng | Manufacturing Engineering Group
CaseyA | Andrea Casey | Six Sigma Engineer
RileyP | Paul Riley | Product Engineer
MarshallG | Gary Marshall | Product Engineer
LeeC | Cindy Lee | Product Engineering Specialist
ProductOps | Product Operations Group
HillF | Frank Hill
WestL | Larry West
BaxterS | Sue Baxter
WynnA | Alice Wynn
ProductMktg | Product Marketing Group
LincolnR | Robert Lincoln | Manufacturing Engineer
ShawH | Harry Shaw | Senior Engineering Lead
JacksonL | Lendell Jackson
RickelsS | Sam Rickels
IthanP | Peg Ithan
Corporate | Corporate Resources
Bpmpmo | Business Process PMO
JohnsonR | Rea Johnson
McneillL | Lori McNeil
Operations | Process Operations
BillingsJ | Judy Billings
Chuf | Frank Chu
Contr | External Contractors
Bpm001 | BPM Consultant 1
Bpm002 | BPM Consultant 2
Bpm003 | BPM Consultant 3
FrostB | Ben Frost
CooperP | Peter Cooper
PetersonM | Michelle Peterson
PrescottW | Wayne Prescott
E&C Resources | E&C Resources
Subcontractors | Subcontractor
Trades | Trades
Management | Management
Purchasing | Purchasing Department
Engineering | Engineering Department
Cretefinisher | Concrete Finisher
Admin | Administrator
Fabrication | Fabrication
Elev Inst | Elevator Installer
Elec | Electrician
Floor | Floor and Carpet Layer
Operator | Operator
Plumb | Plumber
FCarp | Finish Carpenter
RCarp | Rough Carpenter
GenLabor | Laborer-Construction
FieldEng | Field Engineer
IrnWrk | Ironworker
FieldEngSnr | Field Eng-Senior
FieldEngAsst | Field Eng-Assistant
Exc | Excavator
KimP | Paul Kim | Design Engineer
YoungJ | Jeff Young | Analyst
PMs | Project Managers
ResnerW | Wendy Resner | Automation Systems Engineer
DesEng | Design Engineer
McGuireO | Owen McGuire, Project Manager
Project Controls | Project Controls | Accounts Manager
InsEng | Instrumentation Engineer
HVAC | HVAC
Millwork Carpentry | Millwork Subcontractor
Thermal Protection | Thermal Protection Subcontractor
Finishes | Finishes & Fit-out Subcontractor
Concrete-Sub | Concrete Foundation Subcontractor
Specialty Metals | Specialty Metal Fabricator Subcontractor
Pools | Pool Installation Subcontractor
Conveying-Sub | Conveying Subcontractor
Fire Suppression | Fire Suppression Subcontractor
Landscaping | Landscaping Subcontractor
Specialties | FF&E Specialties
Drywall | Drywall Subcontractor
Roofing | Roofing Subcontractor
Glass | Glass & Glazing Subcontractor
Paving | Paving & Roadways Subcontractor
Utilities | Utilities Subcontractor
OPTGP | Operations Test Group
INSP | Inspections | Senior Inspector
Hydro | Hydroblaster
Paint | Painter
Material | Material Resources
Test resource | New Resource Name
Test Resource Child | New Resource Name-1
0QTY | Quantity
MH | Man Hours

## TASKRSRC
task_id | rsrc_id | rsrc_units | start_date | end_date
Activity ID | Resource ID | 1 | (*)Start | (*)Finish
WPICON042 | MathisL | 1 | 01-Apr-24 | 07-Apr-24
WPICON039 | AndersonG | 1 | 01-Jan-23 | 06-Jan-23
WPICON050 | VincentI | 1 | 01-Jun-23 | 09-Jun-23
WPICON146 | CharlesM | 1 | 02-Apr-23 | 10-Apr-23
WPICON011 | ZhuS | 1 | 02-Aug-24 | 11-Aug-24
WPICON113 | LaffertyV | 1 | 02-Dec-23 | 05-Dec-23
WPICON148 | BennettC | 1 | 02-Dec-23 | 06-Dec-23
WPICON023 | PaxsonD | 1 | 02-Feb-24 | 12-Feb-24
WPICON145 | SinghD | 1 | 02-Jan-24 | 11-Jan-24
WPICON091 | SharpeD | 1 | 02-Jul-24 | 12-Jul-24
WPICON118 | ITCon | 1 | 02-Mar-23 | 09-Mar-23
WPICON084 | LiR | 1 | 02-Sep-23 | 11-Sep-23
WPICON040 | RiceB | 1 | 03-Apr-23 | 12-Apr-23
WPICON117 | ChopraA | 1 | 03-Apr-23 | 10-Apr-23
WPICON044 | AbrahamM | 1 | 03-Apr-24 | 09-Apr-24
WPICON032 | WrenJ | 1 | 03-Aug-23 | 10-Aug-23
WPICON083 | ATM ENG | 1 | 03-May-23 | 11-May-23
WPICON030 | IT | 1 | 03-May-24 | 12-May-24
WPICON067 | Product Dev | 1 | 03-May-24 | 08-May-24
WPICON009 | ManufEng | 1 | 03-Nov-23 | 09-Nov-23
WPICON081 | CaseyA | 1 | 04-Feb-23 | 10-Feb-23
WPICON004 | RileyP | 1 | 04-Jan-24 | 09-Jan-24
WPICON127 | MarshallG | 1 | 04-Jul-23 | 12-Jul-23
WPICON006 | LeeC | 1 | 05-Aug-23 | 13-Aug-23
WPICON143 | ProductOps | 1 | 05-Aug-23 | 14-Aug-23
WPICON119 | HillF | 1 | 05-Aug-24 | 11-Aug-24
WPICON129 | WestL | 1 | 05-Dec-23 | 12-Dec-23
WPICON120 | BaxterS | 1 | 05-Jun-24 | 09-Jun-24
WPICON137 | WynnA | 1 | 05-Jun-24 | 08-Jun-24
WPICON086 | ProductMktg | 1 | 05-Mar-24 | 14-Mar-24
WPICON020 | LincolnR | 1 | 05-Sep-23 | 10-Sep-23
WPICON062 | ShawH | 1 | 06-Apr-24 | 14-Apr-24
WPICON150 | JacksonL | 1 | 06-Apr-24 | 14-Apr-24
WPICON082 | RickelsS | 1 | 06-Feb-23 | 10-Feb-23
WPICON015 | IthanP | 1 | 06-Jan-23 | 13-Jan-23
WPICON138 | Corporate | 1 | 06-Jul-24 | 09-Jul-24
WPICON116 | Bpmpmo | 1 | 07-Dec-23 | 13-Dec-23
WPICON049 | JohnsonR | 1 | 07-May-24 | 11-May-24
WPICON078 | McneillL | 1 | 07-May-24 | 17-May-24
WPICON141 | Operations | 1 | 07-May-24 | 12-May-24
WPICON122 | BillingsJ | 1 | 08-Jan-23 | 11-Jan-23
WPICON140 | Chuf | 1 | 08-Jul-24 | 18-Jul-24
WPICON022 | Contr | 1 | 08-Jun-23 | 17-Jun-23
WPICON037 | Bpm001 | 1 | 08-Mar-23 | 17-Mar-23
WPICON147 | Bpm002 | 1 | 08-May-23 | 11-May-23
WPICON065 | Bpm003 | 1 | 08-Nov-23 | 17-Nov-23
WPICON046 | FrostB | 1 | 09-Apr-23 | 16-Apr-23
WPICON061 | CooperP | 1 | 09-Dec-23 | 17-Dec-23
WPICON038 | PetersonM | 1 | 09-Feb-24 | 17-Feb-24
WPICON100 | PrescottW | 1 | 09-Jan-24 | 16-Jan-24
WPICON068 | E&C Resources | 1 | 09-Mar-24 | 12-Mar-24
WPICON033 | Subcontractors | 1 | 10-Apr-24 | 17-Apr-24
WPICON144 | Trades | 1 | 10-Aug-24 | 15-Aug-24
WPICON094 | Management | 1 | 10-Feb-24 | 14-Feb-24
WPICON058 | Purchasing | 1 | 10-Jul-23 | 20-Jul-23
WPICON136 | Engineering | 1 | 10-Jun-24 | 16-Jun-24
WPICON001 | Cretefinisher | 1 | 11-Dec-23 | 18-Dec-23
WPICON123 | Admin | 1 | 11-Jun-24 | 14-Jun-24
WPICON021 | Fabrication | 1 | 11-Nov-23 | 18-Nov-23
WPICON054 | Elev Inst | 1 | 11-Sep-23 | 18-Sep-23
WPICON045 | Elec | 1 | 12-Aug-23 | 21-Aug-23
WPICON072 | Floor | 1 | 12-Jul-23 | 21-Jul-23
WPICON064 | Operator | 1 | 12-Jun-24 | 22-Jun-24
WPICON114 | Plumb | 1 | 12-May-23 | 16-May-23
WPICON085 | FCarp | 1 | 12-May-24 | 16-May-24
WPICON055 | RCarp | 1 | 12-Nov-23 | 16-Nov-23
WPICON090 | GenLabor | 1 | 12-Nov-23 | 19-Nov-23
WPICON079 | FieldEng | 1 | 12-Sep-23 | 22-Sep-23
WPICON125 | IrnWrk | 1 | 12-Sep-23 | 21-Sep-23
WPICON080 | FieldEngSnr | 1 | 13-Feb-24 | 22-Feb-24
WPICON010 | FieldEngAsst | 1 | 13-Jan-23 | 21-Jan-23
WPICON107 | Exc | 1 | 13-Jun-24 | 22-Jun-24
WPICON059 | KimP | 1 | 13-Sep-23 | 16-Sep-23
WPICON095 | YoungJ | 1 | 14-Apr-24 | 20-Apr-24
WPICON112 | PMs | 1 | 14-Aug-24 | 21-Aug-24
WPICON066 | ResnerW | 1 | 14-Jul-24 | 20-Jul-24
WPICON012 | DesEng | 1 | 14-Jun-23 | 17-Jun-23
WPICON099 | McGuireO | 1 | 14-Jun-24 | 19-Jun-24
WPICON149 | Project Controls | 1 | 14-Mar-23 | 22-Mar-23
WPICON076 | InsEng | 1 | 14-Oct-23 | 19-Oct-23
WPICON132 | HVAC | 1 | 14-Sep-23 | 24-Sep-23
WPICON017 | Millwork Carpentry | 1 | 15-Apr-23 | 22-Apr-23
WPICON121 | Thermal Protection | 1 | 15-Feb-23 | 21-Feb-23
WPICON063 | Finishes | 1 | 15-Jun-24 | 21-Jun-24
WPICON108 | Concrete-Sub | 1 | 15-May-23 | 21-May-23
WPICON034 | Specialty Metals | 1 | 15-Oct-23 | 20-Oct-23
WPICON070 | Pools | 1 | 16-Jul-24 | 24-Jul-24
WPICON098 | Conveying-Sub | 1 | 16-Mar-24 | 24-Mar-24
WPICON131 | Fire Suppression | 1 | 16-Nov-23 | 26-Nov-23
WPICON005 | Landscaping | 1 | 17-Apr-24 | 27-Apr-24
WPICON134 | Specialties | 1 | 17-Feb-23 | 27-Feb-23
WPICON101 | Drywall | 1 | 17-Jun-24 | 23-Jun-24
WPICON105 | Roofing | 1 | 17-Oct-23 | 22-Oct-23
WPICON115 | Glass | 1 | 18-Apr-23 | 28-Apr-23
WPICON097 | Paving | 1 | 18-Jul-24 | 27-Jul-24
WPICON087 | Utilities | 1 | 19-Apr-23 | 29-Apr-23
WPICON027 | OPTGP | 1 | 19-Jan-24 | 25-Jan-24
WPICON139 | INSP | 1 | 20-Jun-23 | 27-Jun-23
WPICON109 | Hydro | 1 | 20-May-24 | 27-May-24
WPICON013 | Paint | 1 | 20-Sep-23 | 26-Sep-23
WPICON029 | Material | 1 | 21-Apr-24 | 27-Apr-24
WPICON056 | Test resource | 1 | 21-Apr-24 | 24-Apr-24
WPICON073 | Test Resource Child | 1 | 21-Jan-24 | 28-Jan-24
WPICON142 | 0QTY | 1 | 21-Jul-23 | 31-Jul-23
WPICON007 | MH | 1 | 21-Jul-24 | 26-Jul-24
WPICON093 | Resource ID | 1 | 21-Jun-24 | 28-Jun-24
WPICON060 | MathisL | 1 | 21-Mar-24 | 27-Mar-24
WPICON028 | AndersonG | 1 | 21-May-23 | 31-May-23
WPICON135 | VincentI | 1 | 21-Sep-23 | 24-Sep-23
WPICON024 | CharlesM | 1 | 22-Feb-24 | 03-Mar-24
WPICON071 | ZhuS | 1 | 22-Jul-23 | 27-Jul-23
WPICON092 | LaffertyV | 1 | 23-Apr-24 | 28-Apr-24
WPICON053 | BennettC | 1 | 23-Feb-24 | 28-Feb-24
WPICON104 | PaxsonD | 1 | 23-Feb-24 | 28-Feb-24
WPICON128 | SinghD | 1 | 23-Jan-23 | 01-Feb-23
WPICON026 | SharpeD | 1 | 23-May-23 | 28-May-23
WPICON077 | ITCon | 1 | 23-May-24 | 01-Jun-24
WPICON051 | LiR | 1 | 23-Nov-23 | 01-Dec-23
WPICON110 | RiceB | 1 | 24-Apr-24 | 02-May-24
WPICON103 | ChopraA | 1 | 24-Nov-23 | 01-Dec-23
WPICON008 | AbrahamM | 1 | 25-Apr-23 | 01-May-23
WPICON047 | WrenJ | 1 | 25-Apr-23 | 02-May-23
WPICON035 | ATM ENG | 1 | 25-Feb-24 | 03-Mar-24
WPICON130 | IT | 1 | 25-Jul-23 | 01-Aug-23
WPICON031 | Product Dev | 1 | 25-Jul-24 | 28-Jul-24
WPICON075 | ManufEng | 1 | 25-Jun-23 | 30-Jun-23
WPICON074 | CaseyA | 1 | 25-Jun-24 | 04-Jul-24
WPICON126 | RileyP | 1 | 25-May-24 | 01-Jun-24
WPICON069 | MarshallG | 1 | 25-Oct-23 | 30-Oct-23
WPICON102 | LeeC | 1 | 26-Apr-23 | 30-Apr-23
WPICON019 | ProductOps | 1 | 26-Apr-24 | 30-Apr-24
WPICON052 | HillF | 1 | 26-Feb-23 | 06-Mar-23
WPICON124 | WestL | 1 | 27-Apr-23 | 01-May-23
WPICON016 | BaxterS | 1 | 27-Feb-23 | 03-Mar-23
WPICON111 | WynnA | 1 | 27-May-23 | 31-May-23
WPICON096 | ProductMktg | 1 | 28-Apr-23 | 03-May-23
WPICON043 | LincolnR | 1 | 28-Feb-23 | 10-Mar-23
WPICON025 | ShawH | 1 | 28-Jun-23 | 02-Jul-23
WPICON048 | JacksonL | 1 | 28-Mar-23 | 01-Apr-23
WPICON106 | RickelsS | 1 | 28-May-24 | 06-Jun-24
WPICON002 | IthanP | 1 | 29-Apr-23 | 02-May-23
WPICON036 | Corporate | 1 | 29-Apr-24 | 02-May-24
WPICON041 | Bpmpmo | 1 | 29-Aug-23 | 02-Sep-23
WPICON057 | JohnsonR | 1 | 29-Jul-24 | 07-Aug-24
WPICON133 | McneillL | 1 | 29-Jul-24 | 07-Aug-24
WPICON014 | Operations | 1 | 29-Jun-23 | 07-Jul-23
WPICON089 | BillingsJ | 1 | 29-May-23 | 05-Jun-23
WPICON088 | Chuf | 1 | 30-Jul-24 | 06-Aug-24
WPICON003 | Contr | 1 | 30-Mar-24 | 09-Apr-24
WPICON018 | Bpm001 | 1 | 31-Jul-23 | 04-Aug-23
WPIELC038 | Bpm002 | 1 | 01-Apr-23 | 05-Apr-23
WPIELC056 | Bpm003 | 1 | 01-Aug-23 | 07-Aug-23
WPIELC073 | FrostB | 1 | 01-Jun-23 | 05-Jun-23
WPIELC090 | CooperP | 1 | 01-Mar-24 | 07-Mar-24
WPIELC045 | PetersonM | 1 | 01-Sep-23 | 10-Sep-23
WPIELC065 | PrescottW | 1 | 02-Feb-24 | 07-Feb-24
WPIELC097 | E&C Resources | 1 | 02-Mar-23 | 08-Mar-23
WPIELC009 | Subcontractors | 1 | 03-Aug-24 | 07-Aug-24
WPIELC015 | Trades | 1 | 03-Dec-23 | 09-Dec-23
WPIELC086 | Management | 1 | 03-Feb-23 | 13-Feb-23
WPIELC094 | Purchasing | 1 | 03-Feb-24 | 13-Feb-24
WPIELC093 | Engineering | 1 | 04-Feb-24 | 13-Feb-24
WPIELC011 | Cretefinisher | 1 | 04-Jan-24 | 13-Jan-24
WPIELC059 | Admin | 1 | 05-Aug-23 | 11-Aug-23
WPIELC070 | Fabrication | 1 | 06-Apr-24 | 10-Apr-24
WPIELC077 | Elev Inst | 1 | 06-Apr-24 | 16-Apr-24
WPIELC042 | Elec | 1 | 06-Jul-24 | 16-Jul-24
WPIELC002 | Floor | 1 | 06-Jun-23 | 16-Jun-23
WPIELC024 | Operator | 1 | 06-Sep-23 | 10-Sep-23
WPIELC067 | Plumb | 1 | 06-Sep-23 | 10-Sep-23
WPIELC080 | FCarp | 1 | 07-May-24 | 16-May-24
WPIELC017 | RCarp | 1 | 07-Nov-23 | 17-Nov-23
WPIELC076 | GenLabor | 1 | 08-Dec-23 | 14-Dec-23
WPIELC048 | FieldEng | 1 | 08-Jun-24 | 12-Jun-24
WPIELC084 | IrnWrk | 1 | 08-Nov-23 | 12-Nov-23
WPIELC095 | FieldEngSnr | 1 | 09-Apr-24 | 18-Apr-24
WPIELC019 | FieldEngAsst | 1 | 09-Dec-23 | 15-Dec-23
WPIELC016 | Exc | 1 | 10-Apr-24 | 14-Apr-24
WPIELC071 | KimP | 1 | 10-Feb-24 | 16-Feb-24
WPIELC022 | YoungJ | 1 | 10-Jan-23 | 16-Jan-23
WPIELC043 | PMs | 1 | 10-Jul-24 | 15-Jul-24
WPIELC069 | ResnerW | 1 | 12-Aug-23 | 18-Aug-23
WPIELC004 | DesEng | 1 | 12-Aug-24 | 22-Aug-24
WPIELC099 | McGuireO | 1 | 12-Mar-23 | 22-Mar-23
WPIELC051 | Project Controls | 1 | 12-Sep-23 | 15-Sep-23
WPIELC087 | InsEng | 1 | 12-Sep-23 | 21-Sep-23
WPIELC074 | HVAC | 1 | 13-Mar-24 | 16-Mar-24
WPIELC040 | Millwork Carpentry | 1 | 14-Jan-24 | 19-Jan-24
WPIELC041 | Thermal Protection | 1 | 14-Jun-24 | 24-Jun-24
WPIELC033 | Finishes | 1 | 14-May-23 | 23-May-23
WPIELC005 | Concrete-Sub | 1 | 15-Aug-24 | 23-Aug-24
WPIELC055 | Specialty Metals | 1 | 15-Jan-24 | 22-Jan-24
WPIELC032 | Pools | 1 | 15-Jul-23 | 23-Jul-23
WPIELC049 | Conveying-Sub | 1 | 15-Jul-23 | 19-Jul-23
WPIELC010 | Fire Suppression | 1 | 15-Nov-23 | 23-Nov-23
WPIELC020 | Landscaping | 1 | 16-Dec-23 | 26-Dec-23
WPIELC081 | Specialties | 1 | 17-Jan-24 | 26-Jan-24
WPIELC068 | Drywall | 1 | 17-Nov-23 | 20-Nov-23
WPIELC052 | Roofing | 1 | 18-Apr-23 | 24-Apr-23
WPIELC036 | Glass | 1 | 18-Jul-24 | 27-Jul-24
WPIELC063 | Paving | 1 | 19-Aug-23 | 22-Aug-23
WPIELC091 | Utilities | 1 | 19-Feb-23 | 23-Feb-23
WPIELC057 | OPTGP | 1 | 19-Feb-24 | 29-Feb-24
WPIELC003 | INSP | 1 | 19-Jan-24 | 24-Jan-24
WPIELC050 | Hydro | 1 | 19-Jan-24 | 28-Jan-24
WPIELC085 | Paint | 1 | 19-Jan-24 | 26-Jan-24
WPIELC034 | Material | 1 | 19-Jul-23 | 22-Jul-23
WPIELC029 | Test resource | 1 | 19-Jul-24 | 22-Jul-24
WPIELC092 | Test Resource Child | 1 | 19-Jul-24 | 28-Jul-24
WPIELC027 | 0QTY | 1 | 20-Apr-23 | 24-Apr-23
WPIELC014 | MH | 1 | 20-Aug-23 | 27-Aug-23
WPIELC079 | Resource ID | 1 | 22-Aug-24 | 29-Aug-24
WPIELC098 | MathisL | 1 | 22-Jan-24 | 27-Jan-24
WPIELC008 | AndersonG | 1 | 22-Jul-24 | 25-Jul-24
WPIELC072 | VincentI | 1 | 23-Apr-23 | 29-Apr-23
WPIELC023 | CharlesM | 1 | 23-Jun-23 | 01-Jul-23
WPIELC044 | ZhuS | 1 | 23-May-24 | 28-May-24
WPIELC001 | LaffertyV | 1 | 23-Sep-23 | 03-Oct-23
WPIELC046 | BennettC | 1 | 24-Aug-23 | 03-Sep-23
WPIELC100 | PaxsonD | 1 | 24-Jan-24 | 31-Jan-24
WPIELC026 | SinghD | 1 | 24-Nov-23 | 04-Dec-23
WPIELC096 | SharpeD | 1 | 24-Oct-23 | 01-Nov-23
WPIELC025 | ITCon | 1 | 24-Sep-23 | 04-Oct-23
WPIELC021 | LiR | 1 | 25-Mar-24 | 29-Mar-24
WPIELC058 | RiceB | 1 | 25-May-24 | 04-Jun-24
WPIELC006 | ChopraA | 1 | 26-Dec-23 | 04-Jan-24
WPIELC088 | AbrahamM | 1 | 26-Feb-24 | 05-Mar-24
WPIELC082 | WrenJ | 1 | 26-Jan-24 | 29-Jan-24
WPIELC012 | ATM ENG | 1 | 26-May-24 | 04-Jun-24
WPIELC013 | IT | 1 | 26-Nov-23 | 30-Nov-23
WPIELC028 | Product Dev | 1 | 27-Feb-23 | 09-Mar-23
WPIELC007 | ManufEng | 1 | 27-Mar-24 | 02-Apr-24
WPIELC018 | CaseyA | 1 | 27-Mar-24 | 02-Apr-24
WPIELC053 | RileyP | 1 | 27-May-23 | 03-Jun-23
WPIELC060 | MarshallG | 1 | 27-Nov-23 | 01-Dec-23
WPIELC062 | LeeC | 1 | 27-Nov-23 | 03-Dec-23
WPIELC031 | ProductOps | 1 | 28-Apr-23 | 02-May-23
WPIELC064 | HillF | 1 | 28-Jul-23 | 03-Aug-23
WPIELC078 | WestL | 1 | 28-Mar-23 | 04-Apr-23
WPIELC047 | BaxterS | 1 | 28-Mar-24 | 01-Apr-24
WPIELC066 | WynnA | 1 | 28-May-24 | 04-Jun-24
WPIELC061 | ProductMktg | 1 | 28-Sep-23 | 05-Oct-23
WPIELC054 | LincolnR | 1 | 29-Dec-23 | 05-Jan-24
WPIELC075 | ShawH | 1 | 29-Mar-24 | 03-Apr-24
WPIELC083 | JacksonL | 1 | 29-Mar-24 | 04-Apr-24
WPIELC030 | RickelsS | 1 | 29-May-23 | 07-Jun-23
WPIELC089 | IthanP | 1 | 29-May-23 | 02-Jun-23
WPIELC035 | Corporate | 1 | 30-Sep-23 | 03-Oct-23
WPIELC039 | Bpmpmo | 1 | 31-Dec-23 | 06-Jan-24
WPIELC037 | JohnsonR | 1 | 31-Mar-23 | 05-Apr-23
WPIFIN030 | McneillL | 1 | 01-Aug-23 | 11-Aug-23
WPIFIN041 | Operations | 1 | 01-Dec-23 | 09-Dec-23
WPIFIN071 | BillingsJ | 1 | 01-Jul-23 | 07-Jul-23
WPIFIN032 | Chuf | 1 | 01-Jul-24 | 05-Jul-24
WPIFIN091 | Contr | 1 | 01-Mar-24 | 10-Mar-24
WPIFIN077 | Bpm001 | 1 | 01-Nov-23 | 04-Nov-23
WPIFIN024 | Bpm002 | 1 | 02-May-23 | 11-May-23
WPIFIN017 | Bpm003 | 1 | 02-May-24 | 06-May-24
WPIFIN013 | FrostB | 1 | 02-Oct-23 | 10-Oct-23
WPIFIN063 | CooperP | 1 | 02-Sep-23 | 10-Sep-23
WPIFIN093 | PetersonM | 1 | 03-Jan-23 | 06-Jan-23
WPIFIN081 | PrescottW | 1 | 04-Dec-23 | 08-Dec-23
WPIFIN004 | E&C Resources | 1 | 04-Feb-23 | 12-Feb-23
WPIFIN016 | Subcontractors | 1 | 04-Jul-24 | 10-Jul-24
WPIFIN044 | Trades | 1 | 04-Jun-24 | 13-Jun-24
WPIFIN009 | Management | 1 | 05-Dec-23 | 09-Dec-23
WPIFIN054 | Purchasing | 1 | 05-May-24 | 15-May-24
WPIFIN018 | Engineering | 1 | 06-Apr-24 | 14-Apr-24
WPIFIN010 | Cretefinisher | 1 | 06-Feb-24 | 09-Feb-24
WPIFIN056 | Admin | 1 | 07-Nov-23 | 13-Nov-23
WPIFIN079 | Fabrication | 1 | 08-Apr-23 | 18-Apr-23
WPIFIN011 | Elev Inst | 1 | 08-Jan-23 | 14-Jan-23
WPIFIN082 | Elec | 1 | 08-Jul-24 | 17-Jul-24
WPIFIN099 | Floor | 1 | 08-Mar-23 | 13-Mar-23
WPIFIN060 | Operator | 1 | 08-Nov-23 | 14-Nov-23
WPIFIN007 | Plumb | 1 | 09-Apr-23 | 18-Apr-23
WPIFIN008 | FCarp | 1 | 09-Jul-24 | 16-Jul-24
WPIFIN048 | RCarp | 1 | 09-May-23 | 15-May-23
WPIFIN026 | GenLabor | 1 | 10-Feb-23 | 14-Feb-23
WPIFIN086 | FieldEng | 1 | 10-Jun-24 | 18-Jun-24
WPIFIN027 | IrnWrk | 1 | 11-Apr-24 | 19-Apr-24
WPIFIN074 | FieldEngSnr | 1 | 11-Feb-24 | 17-Feb-24
WPIFIN014 | FieldEngAsst | 1 | 11-Jan-24 | 15-Jan-24
WPIFIN073 | Exc | 1 | 11-Jul-23 | 17-Jul-23
WPIFIN087 | KimP | 1 | 11-Nov-23 | 20-Nov-23
WPIFIN067 | YoungJ | 1 | 11-Sep-23 | 14-Sep-23
WPIFIN022 | PMs | 1 | 12-May-23 | 16-May-23
WPIFIN037 | ResnerW | 1 | 12-May-23 | 19-May-23
WPIFIN012 | DesEng | 1 | 12-Nov-23 | 15-Nov-23
WPIFIN025 | McGuireO | 1 | 13-Dec-23 | 16-Dec-23
WPIFIN069 | Project Controls | 1 | 13-Jan-23 | 17-Jan-23
WPIFIN096 | InsEng | 1 | 13-Jan-24 | 19-Jan-24
WPIFIN090 | HVAC | 1 | 13-May-23 | 17-May-23
WPIFIN045 | Millwork Carpentry | 1 | 14-Dec-23 | 23-Dec-23
WPIFIN068 | Thermal Protection | 1 | 14-Oct-23 | 17-Oct-23
WPIFIN085 | Finishes | 1 | 15-Apr-23 | 18-Apr-23
WPIFIN070 | Concrete-Sub | 1 | 15-Jan-24 | 19-Jan-24
WPIFIN078 | Specialty Metals | 1 | 15-May-23 | 18-May-23
WPIFIN021 | Pools | 1 | 16-Apr-23 | 26-Apr-23
WPIFIN049 | Conveying-Sub | 1 | 16-Jul-23 | 20-Jul-23
WPIFIN062 | Fire Suppression | 1 | 16-Jun-23 | 24-Jun-23
WPIFIN092 | Landscaping | 1 | 16-Jun-23 | 20-Jun-23
WPIFIN002 | Specialties | 1 | 16-Nov-23 | 23-Nov-23
WPIFIN019 | Drywall | 1 | 16-Nov-23 | 19-Nov-23
WPIFIN066 | Roofing | 1 | 17-Feb-24 | 22-Feb-24
WPIFIN028 | Glass | 1 | 18-Jul-24 | 27-Jul-24
WPIFIN052 | Paving | 1 | 18-Nov-23 | 28-Nov-23
WPIFIN064 | Utilities | 1 | 19-Jul-23 | 28-Jul-23
WPIFIN053 | OPTGP | 1 | 19-Jun-24 | 24-Jun-24
WPIFIN061 | INSP | 1 | 19-Sep-23 | 26-Sep-23
WPIFIN043 | Hydro | 1 | 20-Feb-23 | 28-Feb-23
WPIFIN020 | Paint | 1 | 20-Jul-24 | 25-Jul-24
WPIFIN036 | Material | 1 | 20-Nov-23 | 27-Nov-23
WPIFIN094 | Test resource | 1 | 20-Nov-23 | 25-Nov-23
WPIFIN058 | Test Resource Child | 1 | 21-Apr-23 | 30-Apr-23
WPIFIN050 | 0QTY | 1 | 21-Jan-24 | 25-Jan-24
WPIFIN042 | MH | 1 | 21-Jun-23 | 01-Jul-23
WPIFIN001 | Resource ID | 1 | 22-Apr-24 | 01-May-24
WPIFIN098 | MathisL | 1 | 22-Feb-23 | 03-Mar-23
WPIFIN035 | AndersonG | 1 | 22-Feb-24 | 02-Mar-24
WPIFIN005 | VincentI | 1 | 22-Jan-23 | 27-Jan-23
WPIFIN031 | CharlesM | 1 | 22-Jul-24 | 27-Jul-24
WPIFIN072 | ZhuS | 1 | 22-Jun-23 | 02-Jul-23
WPIFIN100 | LaffertyV | 1 | 23-Apr-23 | 02-May-23
WPIFIN015 | BennettC | 1 | 23-Aug-24 | 01-Sep-24
WPIFIN039 | PaxsonD | 1 | 23-Dec-23 | 28-Dec-23
WPIFIN046 | SinghD | 1 | 23-Feb-24 | 27-Feb-24
WPIFIN003 | SharpeD | 1 | 23-Jan-23 | 28-Jan-23
WPIFIN034 | ITCon | 1 | 23-Jan-23 | 31-Jan-23
WPIFIN080 | LiR | 1 | 23-Jun-23 | 01-Jul-23
WPIFIN095 | RiceB | 1 | 23-May-23 | 27-May-23
WPIFIN065 | ChopraA | 1 | 23-Sep-23 | 27-Sep-23
WPIFIN059 | AbrahamM | 1 | 24-Feb-24 | 04-Mar-24
WPIFIN051 | WrenJ | 1 | 24-Jun-24 | 02-Jul-24
WPIFIN057 | ATM ENG | 1 | 24-May-23 | 31-May-23
WPIFIN023 | IT | 1 | 24-May-24 | 30-May-24
WPIFIN038 | Product Dev | 1 | 25-May-24 | 02-Jun-24
WPIFIN097 | ManufEng | 1 | 26-Dec-23 | 31-Dec-23
WPIFIN084 | CaseyA | 1 | 26-Feb-23 | 02-Mar-23
WPIFIN076 | RileyP | 1 | 26-Jul-24 | 29-Jul-24
WPIFIN033 | MarshallG | 1 | 27-Aug-23 | 05-Sep-23
WPIFIN047 | LeeC | 1 | 27-May-23 | 04-Jun-23
WPIFIN040 | ProductOps | 1 | 28-Feb-23 | 03-Mar-23
WPIFIN075 | HillF | 1 | 28-Jul-23 | 06-Aug-23
WPIFIN088 | WestL | 1 | 28-Jun-24 | 02-Jul-24
WPIFIN089 | BaxterS | 1 | 29-Jan-24 | 04-Feb-24
WPIFIN083 | WynnA | 1 | 29-Jun-23 | 09-Jul-23
WPIFIN006 | ProductMktg | 1 | 30-Jul-23 | 04-Aug-23
WPIFIN055 | LincolnR | 1 | 31-Aug-23 | 08-Sep-23
WPIFIN029 | ShawH | 1 | 31-Mar-24 | 08-Apr-24
WPIMACH017 | JacksonL | 1 | 01-Aug-24 | 11-Aug-24
WPIMACH029 | RickelsS | 1 | 01-Dec-23 | 09-Dec-23
WPIMACH109 | IthanP | 1 | 01-Jan-24 | 05-Jan-24
WPIMACH080 | Corporate | 1 | 02-Aug-23 | 08-Aug-23
WPIMACH042 | Bpmpmo | 1 | 02-Feb-23 | 05-Feb-23
WPIMACH015 | JohnsonR | 1 | 02-Nov-23 | 12-Nov-23
WPIMACH024 | McneillL | 1 | 03-Dec-23 | 12-Dec-23
WPIMACH108 | Operations | 1 | 03-Feb-23 | 12-Feb-23
WPIMACH096 | BillingsJ | 1 | 03-Feb-24 | 10-Feb-24
WPIMACH102 | Chuf | 1 | 03-Jul-24 | 13-Jul-24
WPIMACH013 | Contr | 1 | 03-Mar-24 | 08-Mar-24
WPIMACH094 | Bpm001 | 1 | 03-Nov-23 | 07-Nov-23
WPIMACH034 | Bpm002 | 1 | 03-Sep-23 | 12-Sep-23
WPIMACH123 | Bpm003 | 1 | 04-Apr-24 | 13-Apr-24
WPIMACH053 | FrostB | 1 | 04-Dec-23 | 13-Dec-23
WPIMACH126 | CooperP | 1 | 04-Feb-24 | 11-Feb-24
WPIMACH022 | PetersonM | 1 | 04-May-23 | 13-May-23
WPIMACH089 | PrescottW | 1 | 04-May-24 | 11-May-24
WPIMACH119 | E&C Resources | 1 | 05-Aug-24 | 14-Aug-24
WPIMACH101 | Subcontractors | 1 | 05-Feb-23 | 13-Feb-23
WPIMACH077 | Trades | 1 | 05-Feb-24 | 12-Feb-24
WPIMACH041 | Management | 1 | 05-Jan-23 | 11-Jan-23
WPIMACH036 | Purchasing | 1 | 05-Jul-24 | 15-Jul-24
WPIMACH118 | Engineering | 1 | 05-Jun-23 | 10-Jun-23
WPIMACH127 | Cretefinisher | 1 | 06-Aug-24 | 16-Aug-24
WPIMACH044 | Admin | 1 | 06-Jan-23 | 15-Jan-23
WPIMACH051 | Fabrication | 1 | 06-May-23 | 14-May-23
WPIMACH114 | Elev Inst | 1 | 06-May-24 | 09-May-24
WPIMACH003 | Elec | 1 | 07-Apr-24 | 14-Apr-24
WPIMACH040 | Floor | 1 | 07-Aug-23 | 11-Aug-23
WPIMACH062 | Operator | 1 | 07-Aug-23 | 15-Aug-23
WPIMACH047 | Plumb | 1 | 07-Feb-23 | 12-Feb-23
WPIMACH065 | FCarp | 1 | 07-Mar-24 | 14-Mar-24
WPIMACH031 | RCarp | 1 | 07-Nov-23 | 14-Nov-23
WPIMACH038 | GenLabor | 1 | 08-Aug-23 | 15-Aug-23
WPIMACH112 | FieldEng | 1 | 08-Mar-24 | 13-Mar-24
WPIMACH120 | IrnWrk | 1 | 08-Oct-23 | 14-Oct-23
WPIMACH048 | FieldEngSnr | 1 | 08-Sep-23 | 16-Sep-23
WPIMACH020 | FieldEngAsst | 1 | 09-Feb-24 | 13-Feb-24
WPIMACH067 | Exc | 1 | 09-Feb-24 | 16-Feb-24
WPIMACH103 | KimP | 1 | 09-Jan-23 | 16-Jan-23
WPIMACH056 | YoungJ | 1 | 09-Jun-23 | 15-Jun-23
WPIMACH004 | PMs | 1 | 09-May-23 | 13-May-23
WPIMACH072 | ResnerW | 1 | 10-Aug-24 | 16-Aug-24
WPIMACH007 | DesEng | 1 | 10-Mar-24 | 16-Mar-24
WPIMACH106 | McGuireO | 1 | 11-Jan-23 | 14-Jan-23
WPIMACH037 | Project Controls | 1 | 11-Jul-23 | 19-Jul-23
WPIMACH014 | InsEng | 1 | 11-Jul-24 | 16-Jul-24
WPIMACH064 | HVAC | 1 | 11-Jun-24 | 19-Jun-24
WPIMACH084 | Millwork Carpentry | 1 | 11-Jun-24 | 14-Jun-24
WPIMACH107 | Thermal Protection | 1 | 11-May-24 | 17-May-24
WPIMACH098 | Finishes | 1 | 11-Nov-23 | 15-Nov-23
WPIMACH073 | Concrete-Sub | 1 | 12-Apr-24 | 17-Apr-24
WPIMACH095 | Specialty Metals | 1 | 12-Jan-23 | 16-Jan-23
WPIMACH122 | Pools | 1 | 12-Mar-24 | 18-Mar-24
WPIMACH092 | Conveying-Sub | 1 | 12-Sep-23 | 17-Sep-23
WPIMACH057 | Fire Suppression | 1 | 13-Jun-23 | 17-Jun-23
WPIMACH111 | Landscaping | 1 | 14-Aug-24 | 24-Aug-24
WPIMACH113 | Specialties | 1 | 14-Jul-23 | 24-Jul-23
WPIMACH039 | Drywall | 1 | 14-Jun-24 | 22-Jun-24
WPIMACH016 | Roofing | 1 | 14-Mar-24 | 17-Mar-24
WPIMACH082 | Glass | 1 | 14-Nov-23 | 24-Nov-23
WPIMACH035 | Paving | 1 | 15-Dec-23 | 21-Dec-23
WPIMACH008 | Utilities | 1 | 15-Sep-23 | 22-Sep-23
WPIMACH001 | OPTGP | 1 | 17-Apr-24 | 23-Apr-24
WPIMACH129 | INSP | 1 | 17-Dec-23 | 22-Dec-23
WPIMACH075 | Hydro | 1 | 17-Jan-23 | 27-Jan-23
WPIMACH061 | Paint | 1 | 17-Jul-23 | 22-Jul-23
WPIMACH086 | Material | 1 | 17-Jul-23 | 21-Jul-23
WPIMACH002 | Test resource | 1 | 17-Jun-24 | 27-Jun-24
WPIMACH110 | Test Resource Child | 1 | 17-May-23 | 25-May-23
WPIMACH117 | 0QTY | 1 | 17-May-24 | 27-May-24
WPIMACH074 | MH | 1 | 18-Apr-23 | 24-Apr-23
WPIMACH130 | Resource ID | 1 | 18-Apr-23 | 22-Apr-23
WPIMACH027 | MathisL | 1 | 18-Jul-24 | 23-Jul-24
WPIMACH105 | AndersonG | 1 | 18-Nov-23 | 23-Nov-23
WPIMACH005 | VincentI | 1 | 19-Jan-23 | 24-Jan-23
WPIMACH033 | CharlesM | 1 | 19-Jan-23 | 28-Jan-23
WPIMACH099 | ZhuS | 1 | 19-Jul-24 | 24-Jul-24
WPIMACH063 | LaffertyV | 1 | 19-Mar-23 | 25-Mar-23
WPIMACH128 | BennettC | 1 | 20-Dec-23 | 23-Dec-23
WPIMACH049 | PaxsonD | 1 | 20-Jan-24 | 27-Jan-24
WPIMACH104 | SinghD | 1 | 21-Aug-23 | 25-Aug-23
WPIMACH019 | SharpeD | 1 | 21-Feb-24 | 24-Feb-24
WPIMACH090 | ITCon | 1 | 21-Feb-24 | 29-Feb-24
WPIMACH078 | LiR | 1 | 21-May-23 | 31-May-23
WPIMACH079 | RiceB | 1 | 22-Aug-23 | 29-Aug-23
WPIMACH124 | ChopraA | 1 | 22-Aug-23 | 28-Aug-23
WPIMACH030 | AbrahamM | 1 | 22-Dec-23 | 27-Dec-23
WPIMACH032 | WrenJ | 1 | 22-Jul-24 | 28-Jul-24
WPIMACH125 | ATM ENG | 1 | 22-Jun-23 | 25-Jun-23
WPIMACH021 | IT | 1 | 22-Nov-23 | 25-Nov-23
WPIMACH009 | Product Dev | 1 | 23-Aug-24 | 27-Aug-24
WPIMACH070 | ManufEng | 1 | 23-Jan-24 | 29-Jan-24
WPIMACH060 | CaseyA | 1 | 23-Jun-23 | 03-Jul-23
WPIMACH025 | RileyP | 1 | 23-Nov-23 | 03-Dec-23
WPIMACH050 | MarshallG | 1 | 23-Sep-23 | 02-Oct-23
WPIMACH097 | LeeC | 1 | 24-Apr-23 | 30-Apr-23
WPIMACH052 | ProductOps | 1 | 24-Apr-24 | 30-Apr-24
WPIMACH026 | HillF | 1 | 24-Jan-23 | 03-Feb-23
WPIMACH058 | WestL | 1 | 24-Jul-23 | 29-Jul-23
WPIMACH045 | BaxterS | 1 | 25-Aug-23 | 31-Aug-23
WPIMACH059 | WynnA | 1 | 25-Jan-24 | 01-Feb-24
WPIMACH066 | ProductMktg | 1 | 25-Mar-24 | 01-Apr-24
WPIMACH006 | LincolnR | 1 | 26-Aug-23 | 03-Sep-23
WPIMACH043 | ShawH | 1 | 26-Feb-24 | 29-Feb-24
WPIMACH083 | JacksonL | 1 | 26-Feb-24 | 01-Mar-24
WPIMACH121 | RickelsS | 1 | 26-Jan-24 | 03-Feb-24
WPIMACH068 | IthanP | 1 | 26-Jun-23 | 02-Jul-23
WPIMACH069 | Corporate | 1 | 26-Jun-24 | 29-Jun-24
WPIMACH046 | Bpmpmo | 1 | 27-Apr-23 | 02-May-23
WPIMACH010 | JohnsonR | 1 | 27-Jan-24 | 31-Jan-24
WPIMACH076 | McneillL | 1 | 27-Jan-24 | 05-Feb-24
WPIMACH028 | Operations | 1 | 27-Nov-23 | 03-Dec-23
WPIMACH055 | BillingsJ | 1 | 28-Apr-24 | 04-May-24
WPIMACH071 | Chuf | 1 | 28-Feb-23 | 03-Mar-23
WPIMACH116 | Contr | 1 | 28-Feb-24 | 09-Mar-24
WPIMACH100 | Bpm001 | 1 | 28-Jan-23 | 01-Feb-23
WPIMACH087 | Bpm002 | 1 | 28-Jul-23 | 03-Aug-23
WPIMACH091 | Bpm003 | 1 | 28-Nov-23 | 08-Dec-23
WPIMACH093 | FrostB | 1 | 28-Oct-23 | 06-Nov-23
WPIMACH115 | CooperP | 1 | 28-Oct-23 | 02-Nov-23
WPIMACH081 | PetersonM | 1 | 29-Apr-23 | 05-May-23
WPIMACH085 | PrescottW | 1 | 29-Apr-23 | 03-May-23
WPIMACH011 | E&C Resources | 1 | 29-Apr-24 | 02-May-24
WPIMACH018 | Subcontractors | 1 | 30-Dec-23 | 09-Jan-24
WPIMACH012 | Trades | 1 | 30-Jan-24 | 06-Feb-24
WPIMACH023 | Management | 1 | 30-Mar-24 | 09-Apr-24
WPIMACH054 | Purchasing | 1 | 31-Jan-24 | 05-Feb-24
WPIMACH088 | Engineering | 1 | 31-May-23 | 09-Jun-23
WPIMECH093 | Cretefinisher | 1 | 01-Feb-24 | 08-Feb-24
WPIMECH036 | Admin | 1 | 01-Jul-23 | 05-Jul-23
WPIMECH077 | Fabrication | 1 | 01-May-24 | 06-May-24
WPIMECH023 | Elev Inst | 1 | 02-Apr-23 | 11-Apr-23
WPIMECH034 | Elec | 1 | 02-Aug-24 | 10-Aug-24
WPIMECH092 | Floor | 1 | 02-Feb-23 | 05-Feb-23
WPIMECH089 | Operator | 1 | 02-Feb-24 | 11-Feb-24
WPIMECH042 | Plumb | 1 | 02-Jun-23 | 10-Jun-23
WPIMECH087 | FCarp | 1 | 02-Jun-24 | 11-Jun-24
WPIMECH103 | RCarp | 1 | 02-Mar-24 | 08-Mar-24
WPIMECH078 | GenLabor | 1 | 02-May-24 | 11-May-24
WPIMECH091 | FieldEng | 1 | 03-Apr-23 | 07-Apr-23
WPIMECH047 | IrnWrk | 1 | 03-Feb-23 | 08-Feb-23
WPIMECH048 | FieldEngSnr | 1 | 03-Mar-24 | 13-Mar-24
WPIMECH006 | FieldEngAsst | 1 | 03-May-24 | 07-May-24
WPIMECH043 | Exc | 1 | 04-Apr-23 | 07-Apr-23
WPIMECH013 | KimP | 1 | 04-Feb-23 | 08-Feb-23
WPIMECH069 | YoungJ | 1 | 04-Jul-23 | 14-Jul-23
WPIMECH081 | PMs | 1 | 05-Aug-23 | 08-Aug-23
WPIMECH031 | ResnerW | 1 | 05-Feb-24 | 13-Feb-24
WPIMECH058 | DesEng | 1 | 05-Jan-23 | 14-Jan-23
WPIMECH016 | McGuireO | 1 | 05-Jul-23 | 12-Jul-23
WPIMECH101 | Project Controls | 1 | 05-May-24 | 10-May-24
WPIMECH120 | InsEng | 1 | 05-May-24 | 08-May-24
WPIMECH098 | HVAC | 1 | 06-Apr-23 | 14-Apr-23
WPIMECH020 | Millwork Carpentry | 1 | 06-Apr-24 | 09-Apr-24
WPIMECH102 | Thermal Protection | 1 | 06-Apr-24 | 09-Apr-24
WPIMECH059 | Finishes | 1 | 06-Jan-23 | 10-Jan-23
WPIMECH053 | Concrete-Sub | 1 | 06-Jan-24 | 14-Jan-24
WPIMECH097 | Specialty Metals | 1 | 06-Jun-23 | 13-Jun-23
WPIMECH017 | Pools | 1 | 06-May-23 | 12-May-23
WPIMECH114 | Conveying-Sub | 1 | 06-Oct-23 | 15-Oct-23
WPIMECH064 | Fire Suppression | 1 | 07-Aug-23 | 10-Aug-23
WPIMECH075 | Landscaping | 1 | 07-Feb-24 | 14-Feb-24
WPIMECH028 | Specialties | 1 | 07-Jan-24 | 14-Jan-24
WPIMECH039 | Drywall | 1 | 08-Apr-23 | 17-Apr-23
WPIMECH008 | Roofing | 1 | 08-Jan-23 | 18-Jan-23
WPIMECH021 | Glass | 1 | 08-Jan-24 | 12-Jan-24
WPIMECH088 | Paving | 1 | 08-Jul-23 | 17-Jul-23
WPIMECH033 | Utilities | 1 | 08-Jun-23 | 14-Jun-23
WPIMECH060 | OPTGP | 1 | 08-Oct-23 | 16-Oct-23
WPIMECH062 | INSP | 1 | 09-Aug-24 | 18-Aug-24
WPIMECH085 | Hydro | 1 | 09-Dec-23 | 14-Dec-23
WPIMECH084 | Paint | 1 | 09-Feb-23 | 17-Feb-23
WPIMECH112 | Material | 1 | 09-Jul-23 | 16-Jul-23
WPIMECH118 | Test resource | 1 | 09-Jul-24 | 15-Jul-24
WPIMECH063 | Test Resource Child | 1 | 09-May-24 | 16-May-24
WPIMECH030 | 0QTY | 1 | 09-Oct-23 | 16-Oct-23
WPIMECH074 | MH | 1 | 10-Feb-23 | 17-Feb-23
WPIMECH113 | Resource ID | 1 | 10-Nov-23 | 17-Nov-23
WPIMECH119 | MathisL | 1 | 11-May-23 | 14-May-23
WPIMECH038 | AndersonG | 1 | 12-Dec-23 | 15-Dec-23
WPIMECH115 | VincentI | 1 | 12-Dec-23 | 18-Dec-23
WPIMECH096 | CharlesM | 1 | 12-May-23 | 20-May-23
WPIMECH099 | ZhuS | 1 | 12-Oct-23 | 17-Oct-23
WPIMECH029 | LaffertyV | 1 | 13-Dec-23 | 16-Dec-23
WPIMECH010 | BennettC | 1 | 13-Feb-23 | 22-Feb-23
WPIMECH032 | PaxsonD | 1 | 13-Jul-23 | 21-Jul-23
WPIMECH100 | SinghD | 1 | 13-Jun-24 | 21-Jun-24
WPIMECH094 | SharpeD | 1 | 13-Mar-23 | 23-Mar-23
WPIMECH109 | ITCon | 1 | 13-Sep-23 | 16-Sep-23
WPIMECH117 | LiR | 1 | 14-Jun-23 | 17-Jun-23
WPIMECH066 | RiceB | 1 | 15-Dec-23 | 23-Dec-23
WPIMECH044 | ChopraA | 1 | 15-Jun-24 | 19-Jun-24
WPIMECH110 | AbrahamM | 1 | 15-Mar-23 | 18-Mar-23
WPIMECH019 | WrenJ | 1 | 16-Aug-23 | 23-Aug-23
WPIMECH083 | ATM ENG | 1 | 16-Jun-24 | 25-Jun-24
WPIMECH055 | IT | 1 | 16-May-23 | 21-May-23
WPIMECH107 | Product Dev | 1 | 17-Aug-24 | 24-Aug-24
WPIMECH090 | ManufEng | 1 | 17-Feb-24 | 20-Feb-24
WPIMECH002 | CaseyA | 1 | 17-Jan-23 | 24-Jan-23
WPIMECH095 | RileyP | 1 | 17-Jul-23 | 26-Jul-23
WPIMECH022 | MarshallG | 1 | 17-Jun-23 | 21-Jun-23
WPIMECH082 | LeeC | 1 | 17-May-23 | 25-May-23
WPIMECH037 | ProductOps | 1 | 17-Sep-23 | 20-Sep-23
WPIMECH040 | HillF | 1 | 18-Apr-23 | 24-Apr-23
WPIMECH015 | WestL | 1 | 18-Aug-24 | 26-Aug-24
WPIMECH056 | BaxterS | 1 | 18-Dec-23 | 27-Dec-23
WPIMECH045 | WynnA | 1 | 18-Jan-23 | 27-Jan-23
WPIMECH061 | ProductMktg | 1 | 18-May-24 | 21-May-24
WPIMECH073 | LincolnR | 1 | 19-Jul-24 | 24-Jul-24
WPIMECH012 | ShawH | 1 | 19-Nov-23 | 27-Nov-23
WPIMECH106 | JacksonL | 1 | 20-May-23 | 25-May-23
WPIMECH001 | RickelsS | 1 | 20-May-24 | 24-May-24
WPIMECH005 | IthanP | 1 | 21-Aug-24 | 26-Aug-24
WPIMECH104 | Corporate | 1 | 21-Aug-24 | 25-Aug-24
WPIMECH046 | Bpmpmo | 1 | 21-Feb-24 | 24-Feb-24
WPIMECH054 | JohnsonR | 1 | 21-Jun-23 | 26-Jun-23
WPIMECH071 | McneillL | 1 | 21-Mar-24 | 27-Mar-24
WPIMECH018 | Operations | 1 | 21-May-23 | 24-May-23
WPIMECH065 | BillingsJ | 1 | 22-Jan-23 | 27-Jan-23
WPIMECH009 | Chuf | 1 | 22-Mar-23 | 29-Mar-23
WPIMECH014 | Contr | 1 | 22-May-24 | 26-May-24
WPIMECH011 | Bpm001 | 1 | 22-Nov-23 | 01-Dec-23
WPIMECH007 | Bpm002 | 1 | 23-Jun-23 | 03-Jul-23
WPIMECH068 | Bpm003 | 1 | 24-Aug-23 | 28-Aug-23
WPIMECH116 | FrostB | 1 | 24-Feb-23 | 02-Mar-23
WPIMECH076 | CooperP | 1 | 24-Jan-24 | 29-Jan-24
WPIMECH050 | PetersonM | 1 | 24-Jul-23 | 28-Jul-23
WPIMECH035 | PrescottW | 1 | 24-Jul-24 | 29-Jul-24
WPIMECH057 | E&C Resources | 1 | 25-Apr-23 | 30-Apr-23
WPIMECH003 | Subcontractors | 1 | 25-Dec-23 | 29-Dec-23
WPIMECH004 | Trades | 1 | 25-Mar-24 | 01-Apr-24
WPIMECH070 | Management | 1 | 25-Nov-23 | 01-Dec-23
WPIMECH079 | Purchasing | 1 | 26-Dec-23 | 29-Dec-23
WPIMECH111 | Engineering | 1 | 26-Dec-23 | 04-Jan-24
WPIMECH025 | Cretefinisher | 1 | 26-Feb-24 | 03-Mar-24
WPIMECH026 | Admin | 1 | 26-May-24 | 31-May-24
WPIMECH108 | Fabrication | 1 | 26-May-24 | 02-Jun-24
WPIMECH067 | Elev Inst | 1 | 26-Nov-23 | 04-Dec-23
WPIMECH049 | Elec | 1 | 27-Apr-24 | 07-May-24
WPIMECH086 | Floor | 1 | 28-Apr-24 | 08-May-24
WPIMECH027 | Operator | 1 | 28-Nov-23 | 04-Dec-23
WPIMECH041 | Plumb | 1 | 28-Oct-23 | 31-Oct-23
WPIMECH080 | FCarp | 1 | 29-Aug-23 | 07-Sep-23
WPIMECH051 | RCarp | 1 | 29-Jun-23 | 03-Jul-23
WPIMECH024 | GenLabor | 1 | 29-Sep-23 | 05-Oct-23
WPIMECH052 | FieldEng | 1 | 30-May-23 | 02-Jun-23
WPIMECH105 | IrnWrk | 1 | 30-Nov-23 | 08-Dec-23
WPIMECH072 | FieldEngSnr | 1 | 31-May-24 | 04-Jun-24
WPIPRD053 | FieldEngAsst | 1 | 01-Jul-23 | 05-Jul-23
WPIPRD056 | Exc | 1 | 01-Jul-23 | 06-Jul-23
WPIPRD079 | KimP | 1 | 01-Jun-24 | 04-Jun-24
WPIPRD005 | YoungJ | 1 | 01-May-23 | 04-May-23
WPIPRD006 | PMs | 1 | 02-Aug-23 | 11-Aug-23
WPIPRD048 | ResnerW | 1 | 02-Jan-24 | 10-Jan-24
WPIPRD037 | DesEng | 1 | 03-Apr-24 | 10-Apr-24
WPIPRD076 | McGuireO | 1 | 03-Apr-24 | 10-Apr-24
WPIPRD071 | Project Controls | 1 | 03-Feb-23 | 11-Feb-23
WPIPRD109 | InsEng | 1 | 03-Jun-23 | 13-Jun-23
WPIPRD086 | HVAC | 1 | 03-Mar-23 | 13-Mar-23
WPIPRD045 | Millwork Carpentry | 1 | 03-Mar-24 | 10-Mar-24
WPIPRD013 | Thermal Protection | 1 | 03-May-24 | 08-May-24
WPIPRD063 | Finishes | 1 | 03-Sep-23 | 12-Sep-23
WPIPRD062 | Concrete-Sub | 1 | 04-Apr-23 | 10-Apr-23
WPIPRD010 | Specialty Metals | 1 | 04-Apr-24 | 08-Apr-24
WPIPRD117 | Pools | 1 | 04-Feb-23 | 07-Feb-23
WPIPRD017 | Conveying-Sub | 1 | 04-Jun-23 | 13-Jun-23
WPIPRD119 | Fire Suppression | 1 | 04-Jun-24 | 11-Jun-24
WPIPRD083 | Landscaping | 1 | 05-Feb-23 | 10-Feb-23
WPIPRD034 | Specialties | 1 | 05-Jul-23 | 15-Jul-23
WPIPRD008 | Drywall | 1 | 05-Jun-24 | 15-Jun-24
WPIPRD065 | Roofing | 1 | 05-Nov-23 | 14-Nov-23
WPIPRD047 | Glass | 1 | 05-Oct-23 | 08-Oct-23
WPIPRD098 | Paving | 1 | 06-Apr-23 | 10-Apr-23
WPIPRD096 | Utilities | 1 | 06-Dec-23 | 09-Dec-23
WPIPRD035 | OPTGP | 1 | 06-Jul-23 | 15-Jul-23
WPIPRD112 | INSP | 1 | 06-Jul-23 | 13-Jul-23
WPIPRD016 | Hydro | 1 | 06-Mar-24 | 11-Mar-24
WPIPRD110 | Paint | 1 | 06-Sep-23 | 11-Sep-23
WPIPRD093 | Material | 1 | 07-Mar-23 | 16-Mar-23
WPIPRD104 | Test resource | 1 | 07-May-24 | 12-May-24
WPIPRD064 | Test Resource Child | 1 | 08-Apr-23 | 16-Apr-23
WPIPRD066 | 0QTY | 1 | 08-Jun-23 | 17-Jun-23
WPIPRD113 | MH | 1 | 08-Nov-23 | 11-Nov-23
WPIPRD097 | Resource ID | 1 | 09-Dec-23 | 17-Dec-23
WPIPRD077 | MathisL | 1 | 09-Jun-24 | 16-Jun-24
WPIPRD114 | AndersonG | 1 | 09-Jun-24 | 18-Jun-24
WPIPRD107 | VincentI | 1 | 09-Sep-23 | 15-Sep-23
WPIPRD108 | CharlesM | 1 | 10-Apr-23 | 19-Apr-23
WPIPRD111 | ZhuS | 1 | 10-Dec-23 | 20-Dec-23
WPIPRD118 | LaffertyV | 1 | 10-Dec-23 | 19-Dec-23
WPIPRD072 | BennettC | 1 | 10-Feb-24 | 19-Feb-24
WPIPRD081 | PaxsonD | 1 | 10-Jun-23 | 14-Jun-23
WPIPRD059 | SinghD | 1 | 10-Jun-24 | 17-Jun-24
WPIPRD106 | SharpeD | 1 | 10-Mar-23 | 14-Mar-23
WPIPRD074 | ITCon | 1 | 10-Mar-24 | 20-Mar-24
WPIPRD043 | LiR | 1 | 10-Nov-23 | 13-Nov-23
WPIPRD007 | RiceB | 1 | 11-Aug-24 | 17-Aug-24
WPIPRD004 | ChopraA | 1 | 11-Mar-23 | 21-Mar-23
WPIPRD002 | AbrahamM | 1 | 11-May-24 | 16-May-24
WPIPRD087 | WrenJ | 1 | 11-Sep-23 | 20-Sep-23
WPIPRD012 | ATM ENG | 1 | 12-Jun-23 | 20-Jun-23
WPIPRD036 | IT | 1 | 13-Jan-24 | 18-Jan-24
WPIPRD058 | Product Dev | 1 | 13-Jul-24 | 23-Jul-24
WPIPRD091 | ManufEng | 1 | 13-Jun-24 | 22-Jun-24
WPIPRD020 | CaseyA | 1 | 13-May-23 | 21-May-23
WPIPRD024 | RileyP | 1 | 13-Oct-23 | 17-Oct-23
WPIPRD031 | MarshallG | 1 | 14-Aug-24 | 18-Aug-24
WPIPRD046 | LeeC | 1 | 14-Feb-24 | 23-Feb-24
WPIPRD026 | ProductOps | 1 | 14-Jan-24 | 20-Jan-24
WPIPRD100 | HillF | 1 | 14-Jul-23 | 22-Jul-23
WPIPRD102 | WestL | 1 | 14-May-23 | 22-May-23
WPIPRD103 | BaxterS | 1 | 14-Sep-23 | 21-Sep-23
WPIPRD039 | WynnA | 1 | 15-Jul-24 | 19-Jul-24
WPIPRD057 | ProductMktg | 1 | 15-May-24 | 20-May-24
WPIPRD041 | LincolnR | 1 | 16-Jan-24 | 20-Jan-24
WPIPRD019 | ShawH | 1 | 16-Jun-23 | 24-Jun-23
WPIPRD042 | JacksonL | 1 | 17-Apr-24 | 24-Apr-24
WPIPRD015 | RickelsS | 1 | 17-Aug-23 | 24-Aug-23
WPIPRD022 | IthanP | 1 | 17-Aug-23 | 24-Aug-23
WPIPRD038 | Corporate | 1 | 17-Aug-24 | 26-Aug-24
WPIPRD101 | Bpmpmo | 1 | 17-Dec-23 | 24-Dec-23
WPIPRD073 | JohnsonR | 1 | 17-May-23 | 26-May-23
WPIPRD021 | McneillL | 1 | 17-May-24 | 26-May-24
WPIPRD060 | Operations | 1 | 17-Sep-23 | 22-Sep-23
WPIPRD044 | BillingsJ | 1 | 19-Apr-24 | 27-Apr-24
WPIPRD051 | Chuf | 1 | 19-Apr-24 | 23-Apr-24
WPIPRD014 | Contr | 1 | 19-Aug-24 | 23-Aug-24
WPIPRD050 | Bpm001 | 1 | 19-Jan-24 | 23-Jan-24
WPIPRD054 | Bpm002 | 1 | 20-Jan-23 | 29-Jan-23
WPIPRD052 | Bpm003 | 1 | 20-Jan-24 | 30-Jan-24
WPIPRD029 | FrostB | 1 | 21-Apr-23 | 25-Apr-23
WPIPRD068 | CooperP | 1 | 21-Jan-23 | 29-Jan-23
WPIPRD120 | PetersonM | 1 | 21-May-24 | 27-May-24
WPIPRD099 | PrescottW | 1 | 21-Sep-23 | 30-Sep-23
WPIPRD092 | E&C Resources | 1 | 22-Feb-23 | 01-Mar-23
WPIPRD030 | Subcontractors | 1 | 22-Jul-24 | 27-Jul-24
WPIPRD075 | Trades | 1 | 22-Nov-23 | 26-Nov-23
WPIPRD078 | Management | 1 | 23-Apr-24 | 03-May-24
WPIPRD003 | Purchasing | 1 | 23-Jul-23 | 27-Jul-23
WPIPRD095 | Engineering | 1 | 23-Jul-24 | 30-Jul-24
WPIPRD040 | Cretefinisher | 1 | 23-Mar-23 | 29-Mar-23
WPIPRD116 | Admin | 1 | 23-May-24 | 31-May-24
WPIPRD082 | Fabrication | 1 | 23-Sep-23 | 27-Sep-23
WPIPRD049 | Elev Inst | 1 | 24-Jun-24 | 04-Jul-24
WPIPRD094 | Elec | 1 | 24-Jun-24 | 27-Jun-24
WPIPRD084 | Floor | 1 | 24-Mar-23 | 29-Mar-23
WPIPRD088 | Operator | 1 | 24-Sep-23 | 01-Oct-23
WPIPRD018 | Plumb | 1 | 25-Apr-23 | 01-May-23
WPIPRD070 | FCarp | 1 | 25-Apr-24 | 01-May-24
WPIPRD067 | RCarp | 1 | 25-Jul-23 | 04-Aug-23
WPIPRD089 | GenLabor | 1 | 25-Jun-23 | 02-Jul-23
WPIPRD055 | FieldEng | 1 | 25-May-24 | 03-Jun-24
WPIPRD025 | IrnWrk | 1 | 26-Apr-23 | 01-May-23
WPIPRD027 | FieldEngSnr | 1 | 27-Feb-24 | 02-Mar-24
WPIPRD032 | FieldEngAsst | 1 | 27-Jul-24 | 03-Aug-24
WPIPRD061 | Exc | 1 | 27-Jul-24 | 30-Jul-24
WPIPRD033 | KimP | 1 | 27-Mar-23 | 01-Apr-23
WPIPRD105 | YoungJ | 1 | 27-May-24 | 01-Jun-24
WPIPRD028 | PMs | 1 | 28-Jan-23 | 05-Feb-23
WPIPRD009 | ResnerW | 1 | 28-May-24 | 03-Jun-24
WPIPRD011 | DesEng | 1 | 28-Oct-23 | 02-Nov-23
WPIPRD090 | McGuireO | 1 | 29-Dec-23 | 05-Jan-24
WPIPRD023 | Project Controls | 1 | 29-Jun-24 | 03-Jul-24
WPIPRD115 | InsEng | 1 | 29-Sep-23 | 02-Oct-23
WPIPRD069 | HVAC | 1 | 30-Jul-24 | 05-Aug-24
WPIPRD001 | Millwork Carpentry | 1 | 31-Jan-24 | 07-Feb-24
WPIPRD080 | Thermal Protection | 1 | 31-Jul-24 | 06-Aug-24
WPIPRD085 | Finishes | 1 | 31-Jul-24 | 09-Aug-24

## PROJCOST
task_id | cost_name | TASK__status_code | target_cost | act_cost | remain_cost | total_cost | delete_record_flag
Activity ID | Expense Item | (*)Activity Status | Budgeted Cost | Actual Cost | Remaining Cost | At Completion Cost | Delete This Row

## USERDATA
user_data
UserSettings Do Not Edit
DurationQtyType=QT_Hour ShowAsPercentage=0 SmallScaleQtyType=QT_Hour DateFormat=dd'-'mmm'-'yy CurrencyFormat=US Dollar